## Test_Case
| Project Name | Corporate Internet Banking |  |  | Test Cycle No. | Test Cycle - 1 | Test Cycle - 2
| Module Name | Corporate Admin |  |  | Passed | 150 | 129
| Test Case Version | V-0.0.2 |  |  | Failed | 41 | 23
| Written By | Afrida Rahman |  |  | Not Executed | 16 | 2
| Executed By | Afrida Rahman |  |  | Out of Scope | 10 | 19
| Date | 20/10/2024 |  |  | Total | 217 | 173
#SL | Module | Features | Test Cases Description | Test Data | Expected Result | Actual Result | Remarks | Dev Comments | Test Cycle - 1 | Test Cycle - 2 | Screenshots | Remarks
CA-01 | User Admin | Login | Verify the login screen will appear after clicking on a login link |  | Login Screen should appear after entering login URL | Expected Result |  |  | Passed | Passed
CA-02 |  | Login | Verify that the user will be able to log in with their account with the correct credential. |  | User should login with correct credential |  |  |  | Failed | Passed | https://erainfotechbd-my.sharepoint.com/:i:/p/afrida/EUKJAhPg8LdOiga7wVRtySUBZzhI7ZO5RxwSERPDcEbbtw?e=JpE7MY
CA-03 |  | Login | Verify the error message should display after entering the invalid credentials. |  | Error message should display after entering the invalid credentials. | Not as Expected Result |  |  | Failed | Passed | https://erainfotechbd-my.sharepoint.com/:i:/p/afrida/EUKJAhPg8LdOiga7wVRtySUBZzhI7ZO5RxwSERPDcEbbtw?e=JpE7MY
CA-04 |  | Login | Verify that the password entered should be in encrypted form. |  | Password should be entered in encrypted form | Expected Result |  |  | Passed | Passed
CA-05 |  | Login | Verify that the user can be able to view the password by clicking on the eye icon. |  | After click on eye icon user should view the password | Expected Result |  |  | Passed | Passed
CA-06 |  | Login | Verify that the user will get into their dashboard screen after login in with the correct credentials. |  | After logged in user should show Dashboard Screen | Expected Result |  |  | Passed | Passed
CA-07 |  | Login | Add a captcha/OTP on the login form to prevent the robot attack. |  | Captcha/Send OTP option should present in the Login page |  |  |  | Not Executed | Out of Scope
CA-08 |  | Login | Verify new captcha is generated in case the user adds the wrong captcha. |  | New captcha should be generated if the user adds the wrong captcha. |  |  |  | Not Executed | Out of Scope
CA-09 |  | Login | Verify login is not successful without completing CAPTCHA |  | An error message should be displayed stating that the CAPTCHA must be completed. The user should not be logged in, and no session should be created. | If user don't enter captcha then user is logged in and no error message is showing |  |  | Not Executed | Out of Scope
CA-10 |  | Login | Verify that the CAPTCHA reload function works correctly and refreshes the CAPTCHA image. |  | The new CAPTCHA should be distinct from the previous one (i.e., it should not be the same). |  |  |  | Not Executed | Out of Scope
CA-11 |  | Login | Verify that when a user refreshes the CAPTCHA after entering a response, the previous CAPTCHA response is invalidated, and the user must use the new CAPTCHA to log in. |  | Attempting to submit the login form with the old CAPTCHA response should result in an error message indicating that the CAPTCHA is invalid or has expired. |  |  |  | Not Executed | Out of Scope
CA-12 |  | Login | Verify new OTP is generated in case the user adds the wrong OTP. |  | New OTP should be generated if the user adds the wrong OTP. |  |  |  | Not Executed | Out of Scope
CA-13 |  | Login | Verify an error message should be shown in case the user add wrong OTP. |  | An error message should be shown if the user does not enters the wrong OTP. |  |  |  | Not Executed | Out of Scope
CA-14 |  | Login | Verify that if the user adds the wrong OTP, then a Resend OTP option is available or not |  | There should be a visible option or button to resend the OTP, allowing the user to request a new OTP if user enter wrong OTP |  |  |  | Not Executed | Out of Scope
CA-15 |  | Login | Verify that user id will be Lock after Multiple Invalid Login Attempts |  | 1. After the 5th consecutive invalid attempt, the user account should be locked, and the application should display a message indicating the account is locked for 5 minutes. 2. The user should not be able to log in with valid credentials until the 5-minute lockout period has expired. 3. After waiting 5 minutes, the user should be able to log in successfully with valid credentials. | Not as Expected Result |  |  | Failed | Failed
CA-16 |  | Login | Password Reset Option for First-Time Login |  | Upon successful login, the user is presented with an option to reset their password. | Expected Result |  |  | Passed | Passed
CA-17 |  | Login | Verify that users cannot copy and paste the new password into the confirmation password field during the first-time password change. |  | The paste action should be disabled in the "Confirm Password" field, preventing the user from pasting the new password. | Expected Result | Bank Asia Observation |  | Passed | Passed
CA-18 |  | Login | New Password Complexity Requirements |  | It should have following complexity requirements 1. must be at least 8 characters long. 2. must contain at least one special character. 3. must contain at least one uppercase letter and one lowercase letter. 4. must contain at least one digit. | System don't provide this option: 4. must contain at least one digit. |  |  | Passed | Passed
CA-19 |  | Login | Verify the displayed error message grammar should be correct. |  | Displayed error message grammar should be correct. | Expected Result |  |  | Passed | Passed
CA-20 |  | Others | Verify the login session timeout duration. So, once logged in a user cannot be authenticated for a lifetime. |  | User should not be authenticated for lifetime if session timeout is over | Expected Result |  |  | Passed | Passed
CA-21 |  | Profile Management | Ensure that after logging into the Corporate Internet Banking platform, the top right corner of the interface displays the correct user name and id. |  | The top right corner should display the user’s name and role. | Expected Result |  |  | Passed | Passed
CA-22 |  | Profile Management | Verify that Edit Profile option is correctly working or not |  | Edit Profile Option should correctly working | It is not working right now |  |  | Not Executed | Out of Scope
CA-23 |  | Profile Management | Verify Password Reset Option is correctly working or not |  | Password Reset Option should correctly working | Expected Result |  |  | Passed | Passed
CA-24 |  | Change Password | Invalid old password during Password Change |  | An error message should be displayed: "Old password is incorrect. Access Denied." | But it is showing "Invalid User ID or Password. Access Denied." |  |  | Failed | Passed | error message should be correct, it shoud be old password not match.png
CA-25 |  | Change Password | Verify Reset Password Duration field |  | This filed should be only input number digit. Should not be entered numeric digit | Expected Result |  |  | Passed | Passed
CA-26 |  | Change Password | Verify Reset Password Duration field |  | The input field should reject the negative number. | Expected Result |  |  | Passed | Passed
CA-27 |  | Change Password | Validation for minimum and maximum value for Reset Password Duration field |  | This field's minimum value should be 1 and Maximum value should be 360. | Expected Result |  |  | Passed | Passed
CA-28 |  | Change Password | Ensure that the popup is dynamic and reappears correctly if the user enters an incorrect password again. |  | User should successfully click on buttons if this screen showing any error message | When user click on the Reset button and if user gets any error message then Reset button is not visible. This should need dynamically updated |  |  | Failed | Passed
CA-29 |  | Dashboard | Verify that the User Admin Dashboard displays correct and comprehensive user management information and allows administrators to perform necessary actions efficiently. |  | The User Admin Dashboard should accurately display all user information and enable administrators to efficiently manage users and perform necessary actions. |  |  |  | Not Executed
CA-30 |  | Dashboard | Log in with different administrator roles (if applicable) and verify the access and functionalities available on the dashboard. |  | Access and functionalities should be appropriate to the role of the administrator. Higher-level roles should have more extensive permissions. |  |  |  | Not Executed
CA-31 |  | Dashboard | Checking the shared link (Gmail, Facebook, Twitter, WhatsApp) for Corporate Onboard |  | Shared link should be correct | Currently it's redirect to dashboad |  |  | Failed | Passed | shared api should be correct to the sites in Dashboard.png
CA-32 |  | Dashboard | Checking the shared link (Gmail, Facebook, Twitter, WhatsApp) for Corporate User |  | Shared link should be correct | Currently it's redirect to dashboad |  |  | Failed | Passed | shared api should be correct to the sites in Dashboard.png
CA-33 | Setup Approval Management | Approval | Verify that Setup Approval Management is working properly or not |  | Setup Approval Management Page should working properly | Expected Result |  |  | Passed | Passed
CA-34 | Setup Approval Management | Approval | Verify that the search option is working or not |  | Search option should working properly | Expected Result |  |  | Passed | Passed
CA-35 | Setup Approval Management | Approval | Verify that after creating any Setup, the setup is showing for Setup Approval Management page or not |  | The newly created setup should appear on the Setup Approval Management page. | Expected Result |  |  | Passed | Passed
CA-36 | Setup Approval Management | Approval | Verify that View Details button is working or not |  | View Details should working properly | Expected Result |  |  | Passed | Passed
CA-37 | Setup Approval Management | Approval | Verify that in the View Details all the relevant field's value is showing properly or not |  | All relevant fields should display accurate and up-to-date information corresponding to the data they are supposed to represent. | Corporate ID is not showing |  |  | Failed | Failed | corporate ID is not showing in Approval module.png
CA-38 | Setup Approval Management | Approval | Verify in the View Details, Staus option is perfectly working or not |  | Staus option should be Pending, Approved, Reject and these options should be working fine | Expected Result |  |  | Passed | Passed
CA-39 | Setup Approval Management | Approval | Verify Submit Button and Decide Later button is working perfectly or not |  | Submit button and Decide Later button should be working fine | Expected Result |  |  | Passed | Passed
CA-40 | Setup Approval Management | Approval | Ensure left alignment of Setup column on Approval page |  | The Setup column should be left-aligned within its designated area on the approval page. | Expected Result |  |  | Passed | Passed
CA-41 | Corporate Onboard | Corporate Onboard | Verify that the search option is working or not |  | Search option should work properly | Expected Result |  |  | Passed | Passed
CA-42 | Corporate Onboard | Corporate Onboard | Verify that Back button is working or not |  | Back button should work properly | Expected Result |  |  | Passed | Passed
CA-43 | Corporate Onboard | Corporate Onboard | Verify that View Details button is working or not |  | View Details should work properly | Expected Result |  |  | Passed | Passed
CA-44 | Corporate Onboard | Corporate Onboard | Verify that Delete button is working or not |  | Delete option should be working properly | The delete option works correctly, but when an item is deleted, it is not removed from the database; it only shows as active or inactive. Since we already have an active/inactive option in the system, the item should be completely deleted from the database when the delete action is performed. |  |  | Not Executed | Out of Scope
CA-45 | Corporate Onboard | Corporate Onboard | Verify Add button |  | Add button should work properly | Expected Result |  |  | Passed | Passed
CA-46 | Corporate Onboard | Corporate Onboard | Verify Corporate Name field |  | This field should be varchar type field | Expected Result |  |  | Passed | Passed
CA-47 | Corporate Onboard | Corporate Onboard | Verify Contact Person field |  | This field should be varchar type field | Expected Result |  |  | Passed | Passed
CA-48 | Corporate Onboard | Corporate Onboard | Verify Designation field |  | This field should be varchar type field | Expected Result |  |  | Passed | Passed
CA-49 | Corporate Onboard | Corporate Onboard | Verify Contact No. field |  | This field should be number type | Expected Result |  |  | Passed | Passed
CA-50 | Corporate Onboard | Corporate Onboard | Verify Email field |  | This field should be email type field | Expected Result |  |  | Passed | Passed
CA-51 | Corporate Onboard | Corporate Onboard | Verify Address filed |  | This field should be varchar type field | Expected Result |  |  | Passed | Passed
CA-52 | Corporate Onboard | Corporate Onboard | Verify Reg. No. field |  | This field should be varchar type field | Expected Result |  |  | Passed | Passed
CA-53 | Corporate Onboard | Corporate Onboard | Verify Cancel button |  | Next button should working properly | Expected Result |  |  | Passed | Passed
CA-54 | Corporate Onboard | Corporate Onboard | Verify Next button |  | Reset button should working properly. After click on reset button it should clear all the field | Expected Result |  |  | Passed | Passed
CA-55 | Corporate Onboard | Corporate Onboard | Fetch Contact Person Details from CBS During Onboarding |  | The system successfully fetches and displays the contact person details from CBS without any errors. |  |  |  | Not Executed | Not Executed
CA-56 | Corporate Onboard | Corporate Onboard | Verify that after insert customer id system successfully fetch the relevant data or not |  | After insert customer id system should successfully fetch the relevant data | Expected Result |  |  | Passed | Passed
CA-57 | Corporate Onboard | Corporate Onboard | Verify Approval Authorities filed |  | It should be dropdown list | Expected Result |  |  | Passed | Passed
CA-58 | Corporate Onboard | Corporate Onboard | Verifies that the user cannot create a corporate if the Approval Authorities field is not selected. |  | The system should prevent the event from being created and display an error message indicating that the Approval Authorities field must be selected before creating. | Not as Expected. Wrong Error message showing in uper section |  |  | Failed |  | not selecting approval, error message should be pop-up type in Corporate Onboarding.png
CA-59 | Corporate Onboard | Corporate Onboard | Checking the error message by by giving invalid Customer ID in create Corporate Onboard |  | System should give a pop-up error message. | User needs to scroll uper section to see the error message notification |  |  | Failed |  | error message should be pop-up type in Corporate Onboarding.png
CA-60 | Corporate Onboard | Corporate Onboard | Checking the error message by giving the wrong customer id |  | System should give proper error message | Not as Expected |  |  | Failed |  | for invalid customer id, system should give proper error message.png
CA-61 | Corporate Onboard | Corporate Onboard | Verify that a corporate onboarding attempt fails if the customer ID is already registered. |  | 1. If the customer ID already exists, the onboarding request should be rejected. 2. The application should display an error message indicating that the customer ID is already in use and that duplicate onboarding is not allowed. | Expected Result |  |  | Passed | Passed
CA-62 | Corporate Onboard | Corporate Onboard | Verify prevent duplicate submission of customer ID during Approval Process |  | The system should display an error message indicating that the customer ID is already under review and cannot be submitted again | Expected Result |  |  | Passed | Passed
CA-63
CA-64 | Event Master | Event Master | Verify that the search option is working or not |  | Search option should working properly | Expected Result |  |  | Passed
CA-65 | Event Master | Event Master | Verify that View Details button is working or not |  | View Details should working properly | Expected Result |  |  | Passed
CA-66 | Event Master | Event Master | Verify that Delete button is working or not |  | Delete option should working properly | The delete option works correctly, but when an item is deleted, it is not removed from the database; it only shows as active or inactive. Since we already have an active/inactive option in the system, the item should be completely deleted from the database when the delete action is performed. |  |  | Passed
CA-67 | Event Master | Event Master | Verify Event Name filed |  | It should be varchar type | Expected Result |  |  | Passed
CA-68 | Event Master | Event Master | Verify Approval Authorities filed |  | It should be dropdown list | Expected Result |  |  | Passed
CA-69 | Event Master | Event Master | Verify Approval Authorities by Reject the application request |  | System should give proper notification according to approve or reject the request | Not as Expected |  |  | Failed | wrong error message in Event Creation in Reject the requst from Aproval.png
CA-70 | Event Master | Event Master | Verifies that the user cannot create an event if the Approval Authorities field is not selected. |  | The system should prevent the event from being created and display an error message indicating that the Approval Authorities field must be selected before creating. | It is not showing any error message and created successfully |  |  | Failed | System should not allow user to submit the request without the approval authority in Even Master.png
CA-71 | Event Master | Event Master | Create Event Master with Valid Information |  | If all data is valid, the system should create the event master and display a success message. | Expected Result |  |  | Passed
CA-72 | Event Master | Event Master | Verify Edit Button, and after submit the request checking the Approval module |  | After clicking on the Edit button, the user should successfully edit the information |  |  |  | Failed | without the Approval Authority user can edit the Event Master details.png
CA-73 | Event Master | Event Master | Verify Status field |  | The status field should be a dropdown list and values should be Active and Inactive | Expected Result |  |  | Passed
CA-74 | Event Master | Event Master | Verify Update button |  | After clicking on the Update button, user should successfully updated the edited information | Expected Result |  |  | Passed
CA-75 | Event Master | Event Master | Verifies that newly created event do not display as active or inactive until they are approved. If displayed, they should indicate that they are not approved yet. |  | The newly created item should not show as active or inactive before approval. If it is displayed, it should clearly indicate that it has not been approved yet. | Expected Result |  |  | Passed
CA-76
CA-77 | Role Master | Role Master | Verifies that newly created role do not display as active or inactive until they are approved. If displayed, they should indicate that they are not approved yet. |  | The newly created item should not show as active or inactive before approval. If it is displayed, it should clearly indicate that it has not been approved yet. | If user edit the event and change the status to Y before it goes to the Approver, it should become active immediately. |  |  | Failed | Failed | newly created role should not in the list before approval in Role Master.png
CA-78 | Menu Master | Menu Master | Verify that the search option is working or not |  | Search option should working properly | Expected Result |  |  | Passed | Passed
CA-79 | Menu Master | Menu Master | Verify that View Details button is working or not |  | View Details should working properly | Expected Result |  |  | Passed | Passed
CA-80 | Menu Master | Menu Master | Verify that Delete button is working or not |  | Delete option should working properly | The delete option works correctly, but when an item is deleted, it is not removed from the database; it only shows as active or inactive. Since we already have an active/inactive option in the system, the item should be completely deleted from the database when the delete action is performed. |  |  | Out of Scope | Out of Scope
CA-81 | Menu Master | Menu Master | Create User Master with Valid Information |  | If all data is valid, the system should create the user master and display a success message. | Can't Create Menu. It is showing error message |  |  | Failed | Failed | No list and Menu serial should be validated.png
CA-82 | Menu Master | Menu Master | Verify Menu Name field |  | It should be varchar type and required filed | Expected Result |  |  | Passed | Passed
CA-83 | Menu Master | Menu Master | Verify Menu URL filed |  | It should be dropdown list |  |  |  | Not Executed | Not Executed
CA-84 | Menu Master | Menu Master | Verify Menu Type filed |  | It should be dropdown list | Expected Result |  |  | Passed | Passed
CA-85 | Menu Master | Menu Master | Verify Menu Serial filed |  | It should be number type filed and user should not select input negative number here | It is number type filed and user input negative value here and user can create/edit menu with negative value |  |  | Failed | Failed | No list and Menu serial should be validated.png
CA-86 | Menu Master | Menu Master | Verify Approval Authorities filed |  | It should be dropdown list | It is dropdown list value but dropdown icon is missing here |  |  | Failed | Passed | No list and Menu serial should be validated.png
CA-87 | Menu Master | Menu Master | Verifies that the user cannot create a menu if the Approval Authorities field is not selected. |  | The system should prevent the event from being created and display an error message indicating that the Approval Authorities field must be selected before creating. | It is not showing any error message and created successfully |  |  | Failed | Passed
CA-88 | Menu Master | Menu Master | Verify Edit Button |  | After clicking on the Edit button, the user should successfully edit the information | Expected Result |  |  | Passed | Passed
CA-89 | Menu Master | Menu Master | Verify Status field |  | The status field should be a dropdown list and values should be Active and Inactive | It is not dropdown list now and user is inputting Y/N for Active and Inactive |  |  | Failed | Failed | there should be a drop down list for status change in Menu Master.png
CA-90 | Menu Master | Menu Master | Verify Update button |  | After clicking on the Update button, user should successfully updated the edited information | Expected Result |  |  | Passed | Passed
CA-91 | Menu Master | Menu Master | Checking the updated request from Approval |  | After approval menu master setup can be changed | without the approval system changes themenu |  |  | Failed | Failed | without approval system changes Menu Master setup.png
CA-92 | Menu Master | Menu Master | Verifies that newly created menu do not display as active or inactive until they are approved. If displayed, they should indicate that they are not approved yet. |  | The newly created item should not show as active or inactive before approval. If it is displayed, it should clearly indicate that it has not been approved yet. | If user edit the event and change the status to Y before it goes to the Approver, it should become active immediately. |  |  | Failed | Failed | Menu Master newly created.png
CA-93 | Corporate User ID Creation | Corporate User ID Creation | Verify that the search option is working or not |  | Search option should working properly | Expected Result |  |  | Passed | Passed
CA-94 | Corporate User ID Creation | Corporate User ID Creation | Verify that View Details button is working or not |  | View Details should working properly | Expected Result |  |  | Passed | Passed
CA-95 | Corporate User ID Creation | Corporate User ID Creation | Verify that Delete button is working or not |  | Delete option should working properly | The delete option works correctly, but when an item is deleted, it is not removed from the database; it only shows as active or inactive. Since we already have an active/inactive option in the system, the item should be completely deleted from the database when the delete action is performed. |  |  | Out of Scope | Out of Scope
CA-96 | Corporate User ID Creation | Corporate User ID Creation | Create User Master with Valid Information |  | If all data is valid, the system should create the user master and display a success message. | Expected Result |  |  | Passed | Passed
CA-97 | Corporate User ID Creation | Corporate User ID Creation | Verify Corporate filed |  | It should be dropdown list | Expected Result |  |  | Passed | Passed
CA-98 | Corporate User ID Creation | Corporate User ID Creation | Verify Full Name filed |  | It should be varchar type | Expected Result |  |  | Passed | Passed
CA-99 | Corporate User ID Creation | Corporate User ID Creation | Verify Email field |  | It should be email type field | Expected Result |  |  | Passed | Passed
CA-100 | Corporate User ID Creation | Corporate User ID Creation | Verify Approval Authorities filed |  | It should be dropdown list | Expected Result |  |  | Passed | Passed
CA-101 | Corporate User ID Creation | Corporate User ID Creation | Verifies that the user cannot create a user if the Approval Authorities field is not selected |  | The system should prevent the event from being created and display an error message indicating that the Approval Authorities field must be selected before creating. |  |  |  | Failed | Passed | without the approval authority system shows wrong error message.png
CA-102 | Corporate User ID Creation | Corporate User ID Creation | Verify Edit Button |  | After clicking on the Edit button, the user should successfully edit the information | Expected Result |  |  | Passed | Passed
CA-103 | Corporate User ID Creation | Corporate User ID Creation | Verify Status field |  | The status field should be a dropdown list and values should be Active and Inactive | Expected Result |  |  | Passed | Passed
CA-104 | Corporate User ID Creation | Corporate User ID Creation | Verify Update button |  | After clicking on the Update button, user should successfully updated the edited information | Expected Result |  |  | Passed | Passed
CA-105 | Corporate User ID Creation | Corporate User ID Creation | Checking "Access Start Time" and "Access End Time" is validate number |  | Access Start Time and Access End Time should be between 0000 to 2359 |  |  |  | Failed | Failed | Start and STop time should be valid in COrporate ID Creation.png
CA-106 | Corporate User ID Creation | Corporate User ID Creation | Checking the user by Reject the ID creation request |  | Error message should be correct |  |  |  | Failed | Failed | rejecting a customer id notification error should be correct.png
CA-107 | Corporate User ID Creation | Corporate User ID Creation | Checking the alignment |  | Allignment should be correct in Customer Id Creation |  |  |  | Failed | Failed | Allignment should be correct in Customer Id Creation.png
CA-108 | User Rights Allocation | User Rights Allocation | Verify that the search option is working or not |  | Search option should working properly | Expected Result |  |  | Passed | Passed
CA-109 | User Rights Allocation | User Rights Allocation | Verify that View Details button is working or not |  | View Details should working properly | Expected Result |  |  | Passed | Passed
CA-110 | User Rights Allocation | User Rights Allocation | Verify that Delete button is working or not |  | Delete option should working properly | The delete option works correctly, but when an item is deleted, it is not removed from the database; it only shows as active or inactive. Since we already have an active/inactive option in the system, the item should be completely deleted from the database when the delete action is performed. |  |  | Out of Scope | Out of Scope
CA-111 | User Rights Allocation | User Rights Allocation | Create User Rights with Valid Information |  | If all data is valid, the system should create the user rights and display a success message. | Expected Result |  |  | Passed | Passed
CA-112 | User Rights Allocation | User Rights Allocation | Verify Corporate filed |  | It should be dropdown list | Expected Result |  |  | Passed | Passed
CA-113 | User Rights Allocation | User Rights Allocation | Verify User field |  | It should be dropdown list and this field's values should not visible if user don't select Corporate field | It is dropdown list but if user don't select corporate then all the user is showing here. It should be prevent |  |  | Failed | Failed | without selecting Corporate system shoyld not allow user to give User Rights.png
CA-114 | User Rights Allocation | User Rights Allocation | Verify Menu field |  | It should be dropdown list | Expected Result |  |  | Passed | Passed
CA-115 | User Rights Allocation | User Rights Allocation | Verify Approval Authorities filed |  | It should be dropdown list | Expected Result |  |  | Passed | Passed
CA-116 | User Rights Allocation | User Rights Allocation | Verifies that the user cannot create a user if the Approval Authorities field is not selected. |  | The system should prevent the event from being created and display an error message indicating that the Approval Authorities field must be selected before creating. | Expected Result |  |  | Passed | Passed
CA-117 | User Rights Allocation | User Rights Allocation | Verify Edit Button |  | After clicking on the Edit button, the user should successfully edit the information | Expected Result |  |  | Passed | Passed
CA-118 | User Rights Allocation | User Rights Allocation | Verify Status field |  | The status field should be a dropdown list and values should be Active and Inactive | It is not dropdown list now and user is inputting Y/N for Active and Inactive |  |  | Failed | Failed | user Right Allocation active, inactive status drop down list.png
CA-119 | User Rights Allocation | User Rights Allocation | Verify Update button |  | After clicking on the Update button, user should successfully updated the edited information | It is updated but here is a field name called Branch Code. It is required field here, if user don't insert anything in this field then it is also updated successfully. This should not be happened |  |  | Failed | Failed | without approval system changes User Rights setup.png
CA-120 | User Rights Allocation | User Rights Allocation | Verifies that newly created a user rights do not display as active or inactive until they are approved. If displayed, they should indicate that they are not approved yet. |  | The newly created item should not show as active or inactive before approval. If it is displayed, it should clearly indicate that it has not been approved yet. | If user edit the event and change the status to Y before it goes to the Approver, it should become active immediately. |  |  | Failed | Failed | without approval system should not add new user to the list of User Rights module.png
CA-121 | User Rights Allocation | User Rights Allocation | Verifies that users with inactive rights cannot access or view menus associated with those rights. |  | The system should not display the menu items associated with the inactive user rights. If the menu is visible, it should not be accessible, and the user should receive a message indicating that they do not have the necessary permissions to view that menu. | If my user rights are inactive, I should not be able to access the menu associated with those rights. However, I am still able to see the menu, which should not happen. |  |  | Failed | Failed | without approval system should not add new user to the list of User Rights module.png
CA-122 | User Rights Group | User Rights Group | Verify that the search option is working or not |  | Search option should working properly | Expected Result |  |  | Passed | Passed
CA-123 | User Rights Group | User Rights Group | Verify that View Details button is working or not |  | View Details should working properly | Expected Result |  |  | Passed | Passed
CA-124 | User Rights Group | User Rights Group | Verify that Delete button is working or not |  | Delete option should working properly | The delete option works correctly, but when an item is deleted, it is not removed from the database; it only shows as active or inactive. Since we already have an active/inactive option in the system, the item should be completely deleted from the database when the delete action is performed. |  |  | Out of Scope | Out of Scope
CA-125 | User Rights Group | User Rights Group | Create User Rights Group with Valid Information |  | If all data is valid, the system should create the user rights group and display a success message. | Expected Result |  |  | Passed | Passed
CA-126 | User Rights Group | User Rights Group | Verify Role field |  | It should be dropdown list and Only the active roles in the role master menu should be shown in this field | Expected Result |  |  | Passed | Passed
CA-127 | User Rights Group | User Rights Group | Verify Menu field |  | It should be dropdown list and Only the active roles in the role master menu should be shown in this field | Expected Result |  |  | Passed | Passed
CA-128 | User Rights Group | User Rights Group | Verify Approval Authorities filed |  | It should be dropdown list | Expected Result |  |  | Passed | Passed
CA-129 | User Rights Group | User Rights Group | Verifies that the user cannot create a menu if the Approval Authorities field is not selected. |  | The system should prevent the event from being created and display an error message indicating that the Approval Authorities field must be selected before creating. | Expected Result |  |  | Passed | Passed
CA-130 | User Rights Group | User Rights Group | Verify Edit Button |  | After clicking on the Edit button, the user should successfully edit the information | Here Role ID and Menu ID is not needed. Here, user need Role name and Menu name |  |  | Passed | Passed
CA-131 | User Rights Group | User Rights Group | Verify Status field |  | The status field should be a dropdown list and values should be Active and Inactive | It is not dropdown list now and user is inputting Y/N for Active and Inactive |  |  | Failed | Failed
CA-132 | User Rights Group | User Rights Group | Verify Update button |  | After clicking on the Update button, user should successfully updated the edited information | Expected Result |  |  | Passed | Passed
CA-133 | User Rights Group | User Rights Group | Verifies that newly created a user rights group do not display as active or inactive until they are approved. If displayed, they should indicate that they are not approved yet. |  | The newly created item should not show as active or inactive before approval. If it is displayed, it should clearly indicate that it has not been approved yet. | If user edit the event and change the status to Y before it goes to the Approver, it should become active immediately. |  |  | Failed | Failed | without approval system should not add new user to the list of User Rights Group module.png
CA-134 | Assign Roles | Assign Roles | Verify that the search option is working or not |  | Search option should working properly | Expected Result |  |  | Passed | Passed
CA-135 | Assign Roles | Assign Roles | Verify that View Details button is working or not |  | View Details should working properly | Expected Result |  |  | Passed | Passed
CA-136 | Assign Roles | Assign Roles | Verify that Delete button is working or not |  | Delete option should working properly | The delete option works correctly, but when an item is deleted, it is not removed from the database; it only shows as active or inactive. Since we already have an active/inactive option in the system, the item should be completely deleted from the database when the delete action is performed. |  |  | Out of Scope | Out of Scope
CA-137 | Assign Roles | Assign Roles | Create Assign Roles with Valid Information |  | If all data is valid, the system should create the assign roles and display a success message. | Expected Result |  |  | Passed | Passed
CA-138 | Assign Roles | Assign Roles | Verify Corporate filed |  | It should be dropdown list | Expected Result |  |  | Passed | Passed
CA-139 | Assign Roles | Assign Roles | Verify User field |  | It should be dropdown list and this field's values should not visible if user don't select Corporate field | It is dropdown list but if user don't select corporate then all the user is showing here. It should be prevent |  |  | Failed | Failed | all the user list is showing if Corporate is not selected befor in Assign User Roles.png
CA-140 | Assign Roles | Assign Roles | Verify Role field |  | It should be dropdown list | Expected Result |  |  | Passed | Passed
CA-141 | Assign Roles | Assign Roles | Verify Approval Authorities filed |  | It should be dropdown list | Expected Result |  |  | Passed | Passed
CA-142 | Assign Roles | Assign Roles | Verifies that the user cannot create assign roles if the Approval Authorities field is not selected. |  | The system should prevent the event from being created and display an error message indicating that the Approval Authorities field must be selected before creating. | Expected Result |  |  | Passed | Passed
CA-143 | Workflow | Workflow | Verify that the search option is working or not |  | Search option should working properly | Expected Result |  |  | Passed | Passed
CA-144 | Workflow | Workflow | Verify that View Details button is working or not |  | View Details should working properly | Expected Result |  |  | Passed | Passed
CA-145 | Workflow | Workflow | Verify that Delete button is working or not |  | Delete option should working properly | The delete option works correctly, but when an item is deleted, it is not removed from the database; it only shows as active or inactive. Since we already have an active/inactive option in the system, the item should be completely deleted from the database when the delete action is performed. |  |  | Out of Scope | Out of Scope
CA-146 | Workflow | Workflow | Create Workflow with Valid Information |  | If all data is valid, the system should create the workflow and display a success message. | Expected Result |  |  | Passed | Passed
CA-147 | Workflow | Workflow | Verify Corporate filed |  | It should be dropdown list | Expected Result |  |  | Passed | Passed
CA-148 | Workflow | Workflow | Verify Workflow Name field |  | It should be varchar type | Expected Result |  |  | Passed | Passed
CA-149 | Workflow | Workflow | Verify Amount Range field |  |  | Expected Result |  |  | Passed | Passed
CA-150 | Workflow | Workflow | Verify Maker field |  |  | Expected Result |  |  | Passed | Passed
CA-151 | Workflow | Workflow | Verify Checker filed |  | It should be dropdown list | Expected Result |  |  | Passed | Passed
CA-152 | Workflow | Workflow | Verify Approvers filed |  | It should be dropdown list | Expected Result |  |  | Passed | Passed
CA-153 | Workflow | Workflow | Verify Approval Authorities filed |  | It should be dropdown list | Expected Result |  |  | Passed | Passed
CA-154 | Workflow | Workflow | Verifies that the user cannot create assign roles if the Approval Authorities field is not selected. |  | The system should prevent the event from being created and display an error message indicating that the Approval Authorities field must be selected before creating. | Expected Result |  |  | Passed | Passed
CA-155 | Event Wise Workflow | Event Wise Workflow | Verify that the search option is working or not |  | Search option should working properly | Expected Result |  |  | Passed | Passed
CA-156 | Event Wise Workflow | Event Wise Workflow | Verify that View Details button is working or not |  | View Details should working properly | Expected Result |  |  | Passed | Passed
CA-157 | Event Wise Workflow | Event Wise Workflow | Verify that Delete button is working or not |  | Delete option should working properly | Expected Result |  |  | Out of Scope | Out of Scope
CA-158 | Event Wise Workflow | Event Wise Workflow | Create Event Wise Workflow with Valid Information |  | If all data is valid, the system should create the event wise workflow and display a success message. | Expected Result |  |  | Passed | Passed
CA-159 | Event Wise Workflow | Event Wise Workflow | Checking to update and checking the approval option works properly |  | System should not allow user to update the status without the approval | Not as Expected |  |  | Failed | Failed | without the Approval Authority user can edit the Event Wise Workflows details.png
CA-160 | Event Wise Workflow | Event Wise Workflow | Checking to edit the options in dropdown |  | System should not allow user to add text on the dropdown options | Not as Expected |  |  | Failed | Failed | drop down options should not be edited in Event Wise Workflows.png
CA-161 | Assign Roles | Assign Admin Roles | Verify that the search option is working or not |  | Search option should working properly | Expected Result |  |  | Passed | Passed
CA-162 | Assign Roles | Assign Admin Roles | Verify that View Details button is working or not |  | View Details should working properly | Expected Result |  |  | Passed | Passed
CA-163 | Assign Roles | Assign Admin Roles | Verify that Delete button is working or not |  | Delete option should working properly | The delete option works correctly, but when an item is deleted, it is not removed from the database; it only shows as active or inactive. Since we already have an active/inactive option in the system, the item should be completely deleted from the database when the delete action is performed. |  |  | Out of Scope | Out of Scope
CA-164 | Assign Roles | Assign Admin Roles | Create Assign Roles with Valid Information |  | If all data is valid, the system should create the assign roles and display a success message. | Expected Result |  |  | Passed | Passed
CA-165 | Assign Roles | Assign Admin Roles | Verify User field |  | It should be dropdown list | Expected Result |  |  | Passed | Passed
CA-166 | Assign Roles | Assign Admin Roles | Verify Role field |  | It should be dropdown list | Expected Result |  |  | Passed | Passed
CA-167 | Assign Roles | Assign Admin Roles | Verify Approval Authorities filed |  | It should be dropdown list | Expected Result |  |  | Passed | Passed
CA-168 | Assign Roles | Assign Admin Roles | Verifies that the user cannot create assign roles if the Approval Authorities field is not selected. |  | The system should prevent the event from being created and display an error message indicating that the Approval Authorities field must be selected before creating. | Expected Result |  |  | Passed | Passed
CA-169 | Assign Roles | Assign Admin Roles | Checking Cancel button working properly |  | System should allow user to cancle the request | Expected Result |  |  | Passed | Passed
CA-170 | Assign Roles | Assign Admin Roles | Checking Create button working properly |  | System should allow user to submit the request | Expected Result |  |  | Passed | Passed
CA-171 | Back Office | Back Office Users | Verify that the search option is working or not |  | Search option should working properly | Expected Result |  |  | Passed | Passed
CA-172 | Back Office | Back Office Users | Verify that View Details button is working or not |  | View Details should working properly | Expected Result |  |  | Passed | Passed
CA-173 | Back Office | Back Office Users | Verify that Delete button is working or not |  | Delete option should working properly | The delete option works correctly, but when an item is deleted, it is not removed from the database; it only shows as active or inactive. Since we already have an active/inactive option in the system, the item should be completely deleted from the database when the delete action is performed. |  |  | Out of Scope | Out of Scope
CA-174 | Back Office | Back Office Users | Create Assign Roles with Valid Information |  | If all data is valid, the system should create the assign roles and display a success message. | Expected Result |  |  | Passed | Passed
CA-175 | Back Office | Back Office Users | Checking the Update the information |  | Update button should work properly, and without the Approval selection system should pop-up an error message |  |  |  | Failed | Failed | Update should be work properly and without authorization selection, system should give an error message in Back Office Users.png
CA-176 | Back Office | Back Office Users | Verify User field |  | It should be dropdown list | Expected Result |  |  | Passed | Passed
CA-177 | Back Office | Back Office Users | Verify Role field |  | It should be dropdown list | Expected Result |  |  | Passed | Passed
CA-178 | Back Office | Back Office Users | Verify Approval Authorities filed |  | It should be dropdown list | Expected Result |  |  | Passed | Passed
CA-179 | Back Office | Back Office Users | Verifies that the user cannot create assign roles if the Approval Authorities field is not selected. |  | The system should prevent the event from being created and display an error message indicating that the Approval Authorities field must be selected before creating. | Expected Result |  |  | Passed | Passed
CA-180 | Back Office | Back Office Users | Verify by creating new user. without approval system does not show the new created id in the list |  | Without approval system does not show the new created id in the list | Not as Expected |  |  | Failed | Failed | without approval system should not add new user to the list of Back Office Users module.png
CA-181 | Back Office | Back Office Users | Checking Cancel button working properly |  | System should allow user to cancle the request | Expected Result |  |  | Passed | Passed
CA-182 | Back Office | Back Office Users | Checking Create button working properly |  | System should allow user to submit the request | Expected Result |  |  | Passed | Passed
CA-183 | Back Office | Back Office User Rights | Verify that the search option is working or not |  | Search option should working properly | Expected Result |  |  | Passed
CA-184 | Back Office | Back Office User Rights | Verify that View Details button is working or not |  | View Details should working properly | Expected Result |  |  | Passed
CA-185 | Back Office | Back Office User Rights | Verify that Delete button is working or not |  | Delete option should working properly | The delete option works correctly, but when an item is deleted, it is not removed from the database; it only shows as active or inactive. Since we already have an active/inactive option in the system, the item should be completely deleted from the database when the delete action is performed. |  |  | Out of Scope
CA-186 | Back Office | Back Office User Rights | Create User Rights Group with Valid Information |  | If all data is valid, the system should create the user rights group and display a success message. | Expected Result |  |  | Passed
CA-187 | Back Office | Back Office User Rights | Verify User field |  | It should be dropdown list and Only the active roles in the role master menu should be shown in this field | Expected Result |  |  | Passed
CA-188 | Back Office | Back Office User Rights | Verify Menu field |  | It should be dropdown list and Only the active roles in the role master menu should be shown in this field | Expected Result |  |  | Passed
CA-189 | Back Office | Back Office User Rights | Verify Approval Authorities filed |  | It should be dropdown list | Expected Result |  |  | Passed
CA-190 | Back Office | Back Office User Rights | Verifies that the user cannot create a menu if the Approval Authorities field is not selected. |  | The system should prevent the event from being created and display an error message indicating that the Approval Authorities field must be selected before creating. | Expected Result |  |  | Passed
CA-191 | Back Office | Back Office User Rights | Verify Edit Button |  | After clicking on the Edit button, the user should successfully edit the information | Here Role ID and Menu ID is not needed. Here, user need Role name and Menu name |  |  | Passed
CA-192 | Back Office | Back Office User Rights | Verify Status field |  | The status field should be a dropdown list and values should be Active and Inactive | It is not dropdown list now and user is inputting Y/N for Active and Inactive |  |  | Failed |  | Status should be in a drop down list with Active n Inactive selection, in Back Office User Rights.png
CA-193 | Back Office | Back Office User Rights | Verify Update button |  | After clicking on the Update button, user should successfully updated the edited information | Expected Result |  |  | Passed
CA-194 | Back Office | Back Office User Rights | Verifies that newly created a user rights group do not display as active or inactive until they are approved. If displayed, they should indicate that they are not approved yet. |  | The newly created item should not show as active or inactive before approval. If it is displayed, it should clearly indicate that it has not been approved yet. | If user edit the event and change the status to Y before it goes to the Approver, it should become active immediately. |  |  | Failed |  | newly created role should not in the list before approval in Back Office User Rights.png
CA-195 | Transaction | Transaction History | Checking Transaction history from a certain date |  | System should show a list between that period of time | Expected Result |  |  | Passed
CA-196 | Transaction | Transaction History | Checking "To Date" greater than the "From Date" |  | System shouldn't allow user to set "To date greater than the Form Date | Expected Result |  |  | Passed
CA-197 | Transaction | Transaction History | Checking "Reset" button works properly |  | Reset button should reset the given date | Expected Result |  |  | Passed
CA-198 | Transaction | Transaction History | Checking "Search" button works properly |  | Search button should search the transaction between the set date | Expected Result |  |  | Passed
CA-199 | Transaction | Transaction History | Transaction heading and the informations should be in right format with alignment |  | Heading and the information should be in right format with proper alignment | Expected Result |  |  | Passed
CA-200 | Transaction | Transaction History | Checking by selecting "Items per page" works properly |  | System should shows information according to selected "Items per page" number | Expected Result |  |  | Passed
CA-201 | Transaction | Transaction History | Checking Back and Reverse icon works properly |  | Back icon should back the pervious Items Reverse icon should shows the next items | Expected Result |  |  | Passed
CA-202 | Corporate Banking | About | Verifying the responsiveness of the page |  | Page should be responsive | Not as Expected |  |  | Failed |  | page should be responsive and icon should be added for selection in About module.png
CA-203 | Corporate Banking | About | Verifying the allingment of the page |  | Context should be in right allingment as per SRS | Expected Result |  |  | Passed
CA-204 | Corporate Banking | About | Checking every module button works properly |  | System should shows context on by selecting modules: General Corporate Finance, Work Order Financing, Export Finance, Project Finance, Cash Management, Syndication Finance | Expected Result |  |  | Passed
CA-205 | Corporate Banking | About | Checking page context according to selected button |  | Page's context should be releated according to the selected button | Expected Result |  |  | Passed
CA-206 | Corporate Banking | Enquiries - Corporate List | Checking "Reset" button works properly |  | Reset button should reset the given date | Expected Result |  |  | Passed | Passed
CA-207 | Corporate Banking | Enquiries - Corporate List | Checking "Search" button works properly |  | Search option should working properly | Expected Result |  |  | Passed | Passed
CA-208 | Corporate Banking | Enquiries - Corporate List | Checking allignment of the each field |  | Allignment should be correct way | Expected Result |  |  | Passed | Passed
CA-209 | Corporate Banking | Enquiries - Corporate List | Checking "Corporate List View" accending or decending order works properly |  | Information should sort according to order | Expected Result |  |  | Passed | Passed
CA-210 | Corporate Banking | Enquiries - Corporate List | Checking "Customer ID, Corporate ID" fields works according to giving id number |  | System should give information according to given id | Expected Result |  |  | Passed | Passed
CA-211 | Corporate Banking | Enquiries - User List | Checking "Reset" button works properly |  | Reset button should reset the given date | Expected Result |  |  | Passed | Passed
CA-212 | Corporate Banking | Enquiries - User List | Checking "Search" button works properly |  | Search option should working properly | Expected Result |  |  | Passed | Passed
CA-213 | Corporate Banking | Enquiries - User List | Checking allignment of the details each field |  | Allignment should be correct way | Expected Result |  |  | Passed | Passed
CA-214 | Corporate Banking | Enquiries - User List | Checking "Corporate List View" accending or decending order works properly |  | Information should sort according to order |  |  |  | Not Executed | Passed
CA-215 | Corporate Banking | Enquiries - User List | Checking "Customer ID, Corporate ID" fields works according to giving id number |  | System should give information according to given id |  |  |  | Not Executed | Passed
CA-216 | Corporate Banking | Enquiries - User Activity | Checking "Reset" button works properly |  | Reset button should reset the given date | Expected Result |  |  | Passed
CA-217 | Corporate Banking | Enquiries - User Activity | Checking "Search" button works properly |  | Search option should working properly | Expected Result |  |  | Passed
CA-218 | Corporate Banking | Enquiries - User Activity | Checking allignment of the details each field |  | Allignment should be correct way | Expected Result |  |  | Passed
CA-219 | Corporate Banking | Enquiries - User Activity | Checking item per page should give according to seleted number | Checking item per page should give according to seleted number | System should shows the information according to selected item per page, seleted number | Expected Result |  |  | Passed

## Report
Test Case Report
Project Name | Corporate Internet Banking
Module Name | Corporate Admin
Test Case Version | V-0.0.2
Written By | Afrida Rahman
Executed By | Afrida Rahman
Date | 20/10/2024
Reviewed By
TEST EXECUTION REPORT
Test Case Cycle No. | PASS | FAIL | Not Executed (has Dependencies for failed cases) | Out Of Scope | Total TC
Cycle - 1 | 150 | 41 | 16 | 10 | 217
Cycle - 2 | 129 | 23 | 2 | 19 | 173
LIMITATIONS
Documents |  |  |  | Received | Useful
FSD |  |  |  | YES | YES
USER STORY |  |  |  | YES | YES
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug_Report_1
SL# | Observation Date | Module | Role | Feature | Bug Description | Expected Result | Actual Result | Attachments TestCycle-1 | Go Live Critical | Issue Type | Delivery Status | Developer Name | Dev Status | Re-Test Status | Tester Name | Test Cycle | Test Start Date | Test End Date
1 | 27/10/2024 | Admin User | Maker | Login | User can login with incorrect credential (password) | User should login with correct credential | Not as expected | admin can login with invalid credential.png https://erainfotechbd-my.sharepoint.com/:i:/p/afrida/EUKJAhPg8LdOiga7wVRtySUBZzhI7ZO5RxwSERPDcEbbtw?e=Ws0VFe | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
2 | 27/10/2024 | Admin User | Maker | Login | There should add a login method. Like: Password with OTP | User should show login method. Like: Password with OTP, Authenticator App, Email Token | Not as expected |  | Critical | Enhancement |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
3 | 27/10/2024 | Admin User | Maker | Login | There should be presented with an option to enter the OTP | Ensure that after clicking on the “Password with OTP” option, the user is presented with a field to enter the OTP. | Not as expected |  | Critical | Enhancement |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
4 | 27/10/2024 | Admin User | Maker | Login | Error message does not display after entering the invalid credentials | Error message should display after entering the invalid credentials | Not as expected | admin can login with invalid credential 1.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
5 | 27/10/2024 | Admin User | Maker | Login | Captcha/Send OTP option should present in the Login page | Add a captcha/OTP on the login form to prevent the robot attack | Not as expected |  | Critical | Enhancement |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
6 | 27/10/2024 | Admin User | Maker | Login | Checking by User id will be Lock after Multiple Invalid Login Attempts | 1. After the 5th consecutive invalid attempt, the user account should be locked, and the application should display a message indicating the account is locked for 5 minutes. 2. The user should not be able to log in with valid credentials until the 5-minute lockout period has expired. 3. After waiting 5 minutes, the user should be able to log in successfully with valid credentials. | Not as expected |  | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
7 | 27/10/2024 | Admin User | Maker | Login | System accept worng password from login after Reset password | System should not accept invalid password to login | Not as expected | after password reset, dont work | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
8 | 28/10/2024 | Admin User | Maker | Change Password | Error message is not correct | System should set an error message if old password is not matched | Not as expected | error message should be correct, it shoud be old password not match.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
9 | 28/10/2024 | Admin User | Maker | Dashboard | Shared link is not working properly(Gmail, Facebook, Twitter, WhatsApp) | Shared link should be correct | Not as expected | shared api should be correct to the sites in Dashboard.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
10 | 28/10/2024 | Admin User | Maker | Corporate User ID Creation | System takes invalid Access Time | Access Start Time and Access End Time should be between 0000 to 2359 | Not as expected | Start and STop time should be valid in COrporate ID Creation.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
11 | 28/10/2024 | Admin User | Approver | Corporate User ID Creation | Wrong error message in Reject the ID creation request- in approval | Approval message should be correct according toapproval status | Not as expected | rejecting a customer id notification error should be correct.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
12 | 28/10/2024 | Admin User | Maker | Corporate User ID Creation | Allignment and information should be easy to view | There should be in a table in Customer ID Creation | Not as expected | There should be in a table in Customer ID Creation.png | Non-Critical | Enhancement |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
13 | 28/10/2024 | Admin User | Maker | Corporate User ID Creation | Checking Time | There should be add a validation in Customer Id Creation | Not as expected | should be add a validation in Customer Id Creation.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
14 | 29/10/2024 | Admin User | Maker | Corporate User ID Creation | Checking the alignment | Alignment should be correct in Customer Id Creation | Not as expected | Allignment should be correct in Customer Id Creation.png | Non-Critical | Enhancement |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
15 | 29/10/2024 | Admin User | Approver | Corporate User ID Creation | Alignment and information should be in a table | The inforamtions should be in a table | Not as expected | There should be in a table in Customer ID Creation in Approval.png | Non-Critical | Enhancement |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
16 | 29/10/2024 | Admin User | Approver | Corporate User ID Creation | user can create a user without the Approval Authorities field selected | The system should prevent the event from being created and display an error message indicating that the Approval Authorities field must be selected before creating | Not as expected | without the approval authority system shows wrong error message.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
17 | 29/10/2024 | Admin User | Maker | Corporate Onboarding | Saved information should be visible | After giving the id, the other saved details should be shown automatically | Not as expected | After giving the id number, system should show the saved information.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
18 | 29/10/2024 | Admin User | Maker | Corporate Onboarding | The error message shows in upper section | System should give a pop-up error message | Not as expected | error message should be pop-up type in Corporate Onboarding.png | Non-Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
19 | 29/10/2024 | Admin User | Maker | Corporate Onboarding | Wrong error message by giving the invalid customer id | System should give proper error message | Not as expected | for invalid customer id, system should give proper error message.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
20 | 29/10/2024 | Admin User | Maker | Corporate Onboarding | Clicking a module again, the system should automatically refresh the page | System should automatically refresh the page | Not as expected |  | Non-Critical | Enhancement |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
21 | 29/10/2024 | Admin User | Maker | Corporate Onboarding | By not selecting "APPROVAL AUTHORITIES", error should be properly | The system should prevent the event from being created and display an error message indicating that the Approval Authorities field must be selected before creating | Not as expected | not selecting approval, error message should be pop-up type in Corporate Onboarding.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
22 | 29/10/2024 | Admin User | Approver | Event Master | Reject the application request shows wrong error message | System should give proper notification according to approve or reject the request | Not as expected | wrong error message in Event Creation in Reject the requst from Aproval.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
23 | 29/10/2024 | Admin User | Maker | Event Master | It is not showing any error message and created successfully, when Approval Authorities field is not selected | The system should prevent the event from being created and display an error message indicating that the Approval Authorities field must be selected before creating | Not as expected | System should not allow user to submit the request without the approval authority in Even Master.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
24 | 29/10/2024 | Admin User | Maker | Event Master | Submit the request by edit an item and checking the Approval module. Eidted request is not shown in Approval module | After clicking on the Edit button, the user should successfully edit the information. Without the Approval authority system should not allow to submit the request | Not as expected | without the Approval Authority user can edit the Event Master details.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
25 | 29/10/2024 | Admin User | Approver | Approval | Reject the application request, system acts like Approve application | System should approve or reject a request and act likewise | Not as expected | rejecting a Role Master request notification error should be correct.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
26 | 30/10/2024 | Admin User | Maker | Role Master | Drop down icon missing in Approval Authorities filed | It should be dropdown list | Not as expected | drop down iconshould be added to Role Master.png | Non-Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
27 | 30/10/2024 | Admin User | Maker | Role Master | Status in text field | Status field should be in drop down with Active and Inactive selection | Not as expected | Status should be in a drop down list with Active n Inactive selection, in Role Master.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
28 | 30/10/2024 | Admin User | Maker | Role Master | Status accept other words and change the status of role master without approval authorization | system should not accept to change the status without the authorization | Not as expected | Status should not changed without the authorization, in Role Master.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
29 | 30/10/2024 | Admin User | Maker | Role Master | Newly created role do not display as active or inactive until they are approved | The newly created item should not show as active or inactive before approval. If it is displayed, it should clearly indicate that it has not been approved yet | Not as expected | newly created role should not in the list before approval in Role Master.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
30 | 30/10/2024 | Admin User | Maker | Menu Master | Missing "APPROVAL AUTHORITIES" list and Menu serial should be validated | If all data is valid, the system should create the user master and display a success message | Not as expected | No list and Menu serial should be validated.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
31 | 30/10/2024 | Admin User | Maker | Menu Master | Without the approval system changes themenu | After approval "approve or Reject" the menu master setup can be changed | Not as expected | without approval system changes Menu Master setup.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
32 | 30/10/2024 | Admin User | Maker | Menu Master | It is not dropdown list now and user is inputting Y/N for Active and Inactive | The status field should be a dropdown list and values should be Active and Inactive | Not as expected | there should be a drop down list for status change in Menu Master.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
33 | 30/10/2024 | Admin User | Maker | Menu Master | Newly created item shows in the list without the approval | System should not shows, newly created item as active or inactive before approval. If it is displayed, it should clearly indicate that it has not been approved yet | Not as expected | Menu Master newly created.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
34 | 30/10/2024 | Admin User | Maker | User Rights Allocation | Without the approval, user successfully updated the edited information | After approval "Approve or Reject" the User Rights setup can be changed | Not as expected | without approval system changes User Rights setup.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
35 | 30/10/2024 | Admin User | Maker | User Rights Allocation | List icon missing in the approval list dropdown section | List icon should be added to the approval list dropdown section | Not as expected | list icon should be added in Approval authorization to User Rights allocation module.png | Non-Critical | Enhancement |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
36 | 30/10/2024 | Admin User | Maker | User Rights Allocation | Newly created item shows in the list without the approval | The newly created item should not show as active or inactive before approval. If it is displayed, it should clearly indicate that it has not been approved yet | Not as expected | without approval system should not add new user to the list of User Rights module.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
37 | 30/10/2024 | Admin User | Maker | User Rights Allocation | It is not dropdown list now and user is inputting Y/N for Active and Inactive | The status field should be a dropdown list and values should be Active and Inactive | Not as expected | user Right Allocation active, inactive status drop down list.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
38 | 30/10/2024 | Admin User | Maker | User Rights Allocation | System accept to submit request without selecting Corporate option field | System should not allow user to submit request without selecting Corporate option field | Not as expected | without selecting Corporate system shoyld not allow user to give User Rights.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
39 | 30/10/2024 | Admin User | Maker | User Rights Group | Newly created item should not show as active or inactive before approval. | The newly created item should not show as active or inactive before approval. If it is displayed, it should clearly indicate that it has not been approved yet | Not as expected | without approval system should not add new user to the list of User Rights Group module.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
40 | 30/10/2024 | Admin User | Maker | Assign User Roles | It is dropdown list but if user don't select corporate then all the user is showing here | It should be dropdown list and this field's values should not visible if user don't select Corporate field | Not as expected | all the user list is showing if Corporate is not selected befor in Assign User Roles.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
41 | 30/10/2024 | Admin User | Maker | Assign User Roles | Newly created item should not show as active or inactive before approval | The newly created item should not show as active or inactive before approval. If it is displayed, it should clearly indicate that it has not been approved yet | Not as expected |  | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
42 | 30/10/2024 | Admin User | Maker | Assign User Roles | It is not dropdown list now and user is inputting Y/N for Active and Inactive | The status field should be a dropdown list and values should be Active and Inactive | Not as expected | Status should be in a drop down list with Active n Inactive selection, in Assign User Rolers.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
43 | 30/10/2024 | Admin User | Maker | Workflows | The error message shows in upper section | System should give a pop-up error message | Not as expected | error message should be pop-up type in Workflows.png | Non-Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
44 | 30/10/2024 | Admin User | Maker | Workflows | Newly created item should not show as active or inactive before approval. | The newly created item should not show as active or inactive before approval. If it is displayed, it should clearly indicate that it has not been approved yet | Not as expected | without approval system should not add new user to the list of Workflows module.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
45 | 30/10/2024 | Admin User | Maker | Workflows | Rejecting a request, system behaves as approved a request | Rejecting request should reject the request and give proper notification message | Not as expected | rejecting a application, system behaves as approval in Workflows.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
46 | 31/10/2024 | Admin User | Maker | Event Wise Workflows | Without the approval system changes the Status (Active/Inactive) | The newly created item should not show as active or inactive before approval. If it is displayed, it should clearly indicate that it has not been approved yet | Not as expected | without the Approval Authority user can edit the Event Wise Workflows details.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
47 | 31/10/2024 | Admin User | Maker | Event Wise Workflows | Checking to edit the options in dropdown | System should not allow user to add text on the dropdown options | Not as expected | drop down options should not be edited in Event Wise Workflows.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
48 | 31/10/2024 | Admin User | Maker | Event Wise Workflows | Error should be specific |  | Not as expected | error should be specific.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
49 | 31/10/2024 | Admin User | Maker | Back Office Users | Checking the Update the information | Update button should work properly, and without the Approval selection system should pop-up an error message | Not as expected | Update should be work properly and without authorization selection, system should give an error message in Back Office Users.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
50 | 31/10/2024 | Admin User | Maker | Back Office Users | Without the approval system shows new created user in the list | Without approval system does not show the new created id in the list | Not as expected | without approval system should not add new user to the list of Back Office Users module.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
51 | 31/10/2024 | Admin User | Maker | Back Office Users | Rejecting a request, system behaves as approved a request | Rejecting request should reject the request and give proper notification message | Not as expected | rejecting a application, system behaves as approval in Back Office Users in Approval.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
52 | 31/10/2024 | Admin User | Maker | Back Office User Rights | Without approval, newly Back Office User Rights should not in the list | The newly created item should not show as active or inactive before approval. If it is displayed, it should clearly indicate that it has not been approved yet | Not as expected | newly created role should not in the list before approval in Back Office User Rights.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
53 | 31/10/2024 | Admin User | Maker | Back Office User Rights | User can input any other character in the Status field | Status should be in drop down list with Active or Inactive oprion | Not as expected | Status should be in a drop down list with Active n Inactive selection, in Back Office User Rights.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
54 | 2024-03-11 | Admin User | Maker | About | Page is not responsive and selection icon missing | Page should be responsive and selection icon should be added | Not as expected | page should be responsive and icon should be added for selection in About module.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
55 | 2024-03-11 | Admin User | Approver | Approval | Corporate ID is not showing | All relevant fields should display accurate and up-to-date information corresponding to the data they are supposed to represent | Not as expected | corporate ID is not showing in Approval module.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11
56 | 2024-03-11 | Admin User | Approver | Approval | Rejecting a request, system behaves as approved a request | Rejecting request should reject the request and give proper notification message | Not as expected | rejecting a application, system behaves as approval in Back Office Users in Approval.png | Critical | Bug |  |  |  |  | Afrida Rahman | 1 | 27/10/2024 | 2024-03-11

## Bug_Report_2
SL# | Observation Date | Module | Role | Feature | Bug Description | Expected Result | Actual Result | Attachments TestCycle-2 | Go Live Critical | Issue Type | Delivery Status | Developer Name | Dev Status | Re-Test Status | Tester Name | Test Cycle | Test Start Date | Test End Date
3 | 13/11/2024 | Admin User | Maker | Login | Error message is not correct after entering the invalid credentials | Error message should be correct by giving invalid credentials | Not as expected | Error message should be correct in Login.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
5 | 14/11/2024 | Admin User | Maker | Change Password | System accept 0 in Time Duration | System should accept 0 number in Time Duration | Not as expected | system allow to reset password with 0 in Duration time in Reset Password.png | Critical | Bug |  |  | Fixed |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
6 | 14/11/2024 | Admin User | Maker | Corporate User ID Creation | Error message is invalid in Access End Time | Access Start Time and Access End Time should be between 0000 to 2359 | Not as expected | error message should be valid.png | Non-Critical | Bug |  |  | Fixed |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
7 | 14/11/2024 | Admin User | Approver | Corporate User ID Creation | Wrong error message in Reject the ID creation request- in approval | Approval message should be correct according toapproval status | Not as expected | Wrong error message in Rejecting a request in approval.png | Critical | Bug |  |  | Fixed |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
8 | 14/11/2024 | Admin User | Maker | Corporate User ID Creation | Clicking "User Details", disapair User ID | System should not disapair any information by clicking in details option | Not as expected | clicking in details,vanishes the user id in User Master ID creation.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
9 | 14/11/2024 | Admin User | Maker | Corporate User ID Creation | Creating user more than 5, system doest not show the previously active user's information | System should not disapair any information by adding new user | Not as expected | creating multiple user more than 5, system doesnot shows previous Active id in User Master ID Creation module.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
10 | 14/11/2024 | Admin User | Maker | Corporate User ID Creation | New user should not added to the list before authority's approval | System should not add new user in the list before approval | Not as expected | new user should not added to the list before approval.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
11 | 14/11/2024 | Admin User | Maker | Corporate User ID Creation | Admin maker can change the status by-self | System should not allow maker admin to change the status | Not as expected | one admin can accept the id creation request by self without others approval in User Master module.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
12 | 14/11/2024 | Admin User | Maker | Corporate User ID Creation | Refresh the page, changes the user status | System should not change the status | Not as expected | refresh the page shows previous status when one admin selfly accept the request in User Master module.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
13 | 14/11/2024 | Admin User | Maker | Corporate User ID Creation | "Select Status" search filter not working for "Inactive" user's | System should shows the information according to the user's status | Not as expected | Select status filter dont work as expected in User Master ID Creation.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
14 | 14/11/2024 | Admin User | Approver | Approval | Reject the application request, system shows approve success message | System should show message according to approve or reject a request and act likewise | Not as expected | Wrong error message in Rejecting a request in approval.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
15 | 14/11/2024 | Admin User | Approver | Approval | Corporate ID is not showing | All relevant fields should display accurate and up-to-date information corresponding to the data they are supposed to represent | Not as expected | id should be visible in Approval module.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
16 | 14/11/2024 | Admin User | Approver | Approval | Rejecting a request, system behaves as approved a request | Rejecting request should reject the request and give proper notification message | Not as expected | Wrong error message in Rejecting a request in approval.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
17 |  | Admin User | Maker | Corporate Onboarding | Saved information should be visible | After giving the id, the other saved details should be shown automatically | Not as expected |  | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 27/10/2024 | 2024-03-11
18 |  | Admin User | Maker | Corporate Onboarding | The error message shows in upper section | System should give a pop-up error message | Not as expected |  | Non-Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 27/10/2024 | 2024-03-11
19 |  | Admin User | Maker | Corporate Onboarding | Wrong error message by giving the invalid customer id | System should give proper error message | Not as expected |  | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 27/10/2024 | 2024-03-11
20 |  | Admin User | Maker | Corporate Onboarding | Clicking a module again, the system should automatically refresh the page | System should automatically refresh the page | Not as expected |  | Non-Critical | Enhancement |  |  |  |  | Afrida Rahman | 2 | 27/10/2024 | 2024-03-11
21 |  | Admin User | Maker | Corporate Onboarding | By not selecting "APPROVAL AUTHORITIES", error should be properly | The system should prevent the event from being created and display an error message indicating that the Approval Authorities field must be selected before creating | Not as expected |  | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 27/10/2024 | 2024-03-11
22 |  | Admin User | Approver | Event Master | Reject the application request shows wrong error message | System should give proper notification according to approve or reject the request | Not as expected |  | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 27/10/2024 | 2024-03-11
23 |  | Admin User | Maker | Event Master | It is not showing any error message and created successfully, when Approval Authorities field is not selected | The system should prevent the event from being created and display an error message indicating that the Approval Authorities field must be selected before creating | Not as expected |  | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 27/10/2024 | 2024-03-11
24 |  | Admin User | Maker | Event Master | Submit the request by edit an item and checking the Approval module. Eidted request is not shown in Approval module | After clicking on the Edit button, the user should successfully edit the information. Without the Approval authority system should not allow to submit the request | Not as expected |  | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 27/10/2024 | 2024-03-11
17 | 14/11/2024 | Admin User | Maker | Role Master | Status in text field | Status field should be in drop down with Active and Inactive selection | Not as expected | status should be in drop down list in Role Master.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
18 | 14/11/2024 | Admin User | Maker | Role Master | Status accept other words and change the status of role master without approval authorization | system should not accept to change the status without the authorization | Not as expected | status should be in drop down list in Role Master.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
19 | 14/11/2024 | Admin User | Maker | Role Master | Newly created role do not display as active or inactive until they are approved | The newly created item should not show as active or inactive before approval. If it is displayed, it should clearly indicate that it has not been approved yet | Not as expected | newly created Role should not added in the list in Role Master.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
20 | 14/11/2024 | Admin User | Maker | Role Master | Maker admin can change the a/c status by-self | System should not allow maker admin to change the status | Not as expected | maker admin can change the status by self without others approval in Role Master.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
21 | 14/11/2024 | Admin User | Maker | Menu Master | Approval authority field should be indicated | System should give an pop-up message for not selecting the Approval authority | Not as expected | approval authority field should be indicated in Menu Master.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
22 | 14/11/2024 | Admin User | Maker | Menu Master | Menu serial should be validated | If all data is valid, the system should create the user master and display a success message | Not as expected | error message should be added for invalid input in Menu Master.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
23 | 14/11/2024 | Admin User | Maker | Menu Master | Without the approval system changes the menu | After approval "approve or Reject" the menu master setup can be changed | Not as expected | without approval maker admin can change the status.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
24 | 14/11/2024 | Admin User | Maker | Menu Master | It is not dropdown list now and user is inputting Y/N for Active and Inactive | The status field should be a dropdown list and values should be Active and Inactive | Not as expected | status should be in drop down list in Menu Master.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
25 | 14/11/2024 | Admin User | Maker | Menu Master | Newly created item shows in the list without the approval | System should not shows, newly created item as active or inactive before approval. If it is displayed, it should clearly indicate that it has not been approved yet | Not as expected | newly created Menu should not added in the list in Menu Master.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
26 | 14/11/2024 | Admin User | Maker | User Rights Allocation | Without the approval, user successfully updated the edited information | After approval "Approve or Reject" the User Rights setup can be changed | Not as expected | maker admin can change the status by self without others approval in User Rights.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
27 | 14/11/2024 | Admin User | Maker | User Rights Allocation | Newly created item shows in the list without the approval | The newly created item should not show as active or inactive before approval. If it is displayed, it should clearly indicate that it has not been approved yet | Not as expected | newly created user should not added in the list in User Rights.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
28 | 14/11/2024 | Admin User | Maker | User Rights Allocation | It is not dropdown list now and user is inputting Y/N for Active and Inactive | The status field should be a dropdown list and values should be Active and Inactive | Not as expected | status should be in drop down list in User Rights.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
29 | 14/11/2024 | Admin User | Maker | User Rights Allocation | System accept to submit request without selecting Corporate option field | System should not allow user to submit request without selecting Corporate option field | Not as expected | without selecting Corporate section maker admin can create User Rights module.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
30 | 14/11/2024 | Admin User | Maker | User Rights Group | Newly created item should not show as active or inactive before approval. | The newly created item should not show as active or inactive before approval. If it is displayed, it should clearly indicate that it has not been approved yet | Not as expected | newly created Users Right should not added in the list in User Riights Group.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
31 | 14/11/2024 | Admin User | Maker | User Rights Group | Status accept other words and change the status | System should not allow user to add text on the dropdown options | Not as expected | status should be in drop down list in User Rights Group.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
40 | 17/11/2024 | Admin User | Maker | Assign Admin Roles | It is dropdown list but if user don't select corporate then all the user is showing here | It should be dropdown list and this field's values should not visible if user don't select Corporate field | Not as expected |  | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
41 | 17/11/2024 | Admin User | Maker | Assign Admin Roles | Newly created item should not show as active or inactive before approval | The newly created item should not show as active or inactive before approval. If it is displayed, it should clearly indicate that it has not been approved yet | Not as expected | newly created user should not added in the list in Assign Admin User Roles.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
42 | 17/11/2024 | Admin User | Maker | Assign Admin Roles | It is not dropdown list now and user is inputting Y/N for Active and Inactive | The status field should be a dropdown list and values should be Active and Inactive | Not as expected | status should be in drop down list in Assign Admin User ROlesr.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
44 | 17/11/2024 | Admin User | Maker | Workflows | Newly created item should not show as active or inactive before approval. | The newly created item should not show as active or inactive before approval. If it is displayed, it should clearly indicate that it has not been approved yet | Not as expected | newly created Workflow item should not added in the list in Workflow.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
45 | 17/11/2024 | Admin User | Maker | Workflows | Rejecting a request, system behaves as approved a request | Rejecting request should reject the request and give proper notification message | Not as expected | rejecting acts like successful in Workflows.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
46 | 17/11/2024 | Admin User | Maker | Workflows | Clicking edit button, system make the user to log out | System should not make the user to log out by clicking the edit button | Not as expected | edit in workflow, make user to log out.png | Critical | Bug | [5 empty] | 2 | 13/11/2024 | 18/11/2024
47 | 17/11/2024 | Admin User | Maker | Event Wise Workflows | Without the approval system changes the Status (Active/Inactive) | The newly created item should not show as active or inactive before approval. If it is displayed, it should clearly indicate that it has not been approved yet | Not as expected | status should be in drop down list in Event Wise Workflows.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
48 | 17/11/2024 | Admin User | Maker | Event Wise Workflows | Checking to edit the options in dropdown | System should not allow user to add text on the dropdown options | Not as expected | dropdown options should not be editable.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
49 | 17/11/2024 | Admin User | Maker | Event Wise Workflows | Maker admin can change the a/c status by-self without approval | System should not allow user to update the information without approval | Not as expected | maker admin can change the status by self without others approval in Event Wise Workflows.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
50 | 17/11/2024 | Admin User | Maker | Back Office Users | Checking the Update the information to Active/Inactive | Update button should work properly and there's should be a option for Status field (Active/Inactive) | Not as expected | there should be option for status update in Back Office Users.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
51 | 17/11/2024 | Admin User | Maker | Back Office Users | Without the approval system shows new created user in the list | Without approval system does not show the new created id in the list | Not as expected | newly created back office user should not added in the list in Back Office Users.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
52 | 17/11/2024 | Admin User | Maker | Back Office Users | Rejecting a request, system behaves as approved a request | Rejecting request should reject the request and give proper notification message | Not as expected | rejecting acts like successful in Back Office Users.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
53 | 17/11/2024 | Admin User | Maker | Back Office User Rights | Without approval, newly Back Office User Rights should not in the list | The newly created item should not show as active or inactive before approval. If it is displayed, it should clearly indicate that it has not been approved yet | Not as expected |  | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
54 | 17/11/2024 | Admin User | Maker | Back Office User Rights | User can input any other character in the Status field | Status should be in drop down list with Active or Inactive oprion | Not as expected |  | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
55 | 18/11/2024 | Admin User | Maker | Enquiries - Corporate List | To Date should be in correct choosen | To Date should be greater than From Date | Not as expected | TO date should be greater than From Date in Corporate List.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024
56 | 18/11/2024 | Admin User | Maker | Enquiries - User List | To Date should be in correct choosen | To Date should be greater than From Date | Not as expected | TO date should be greater than From Date in User List.png | Critical | Bug |  |  |  |  | Afrida Rahman | 2 | 13/11/2024 | 18/11/2024

## Bug_Report_3
SL# | Observation Date | Module | Role | Feature | Bug Description | Expected Result | Actual Result | Attachments TestCycle-2 | Go Live Critical | Issue Type | Delivery Status | Developer Name | Dev Status | Re-Test Status | Tester Name | Test Cycle | Test Start Date | Test End Date
3 | 21/11/2024 | Admin User | Approval | Approver | Corporate ID is not shown | Corporate ID with other Details should be visible | Not as expected | corporate id is not shown in Approval Module.png | Critical | Bug |  |  |  |  | Afrida Rahman | 3 | 21/11/2024