## Test_Cases
| Project Name | Corporate Internet Banking |  |  |  | Test Cycle No. | Test Cycle - 2
| Module Name | Corporate User |  |  |  | Passed | 77
| Test Case Version | V-0.0.2 |  |  |  | Failed | 16
| Written By | Afrida Rahman |  |  |  | Not Executed (has Dependencies for Failed cases) | 24
| Executed By | Afrida Rahman |  |  |  | Out of Scope | 0
| Date | 20/10/2024 |  |  |  | Total | 117
| Reviewed By | N/A
#SL | Module | Features | Test Cases Description | Pre-Condition | Test Data | Expected Result | Actual Result | Test Cycle-2 | Bug Screenshots | Remarks | Dev Comments
CU-0.0.1 |  | Login | Verify the login screen will appear after clicking on a login link |  |  | Login Screen should appear after entering login URL | Expected Result | Passed
CU-0.0.2 |  | Login | Verify that the user will be able to log in with their account with the correct credential. |  |  | User should login with correct credential | Expected Result | Passed
CU-0.0.3 |  | Login | Verify that if user assign roles is not defined then user is login or not |  |  | If user assign roles is not defined then user should not be login in the system. | Expected Result | Passed
CU-0.0.4 |  | Login | Ensure that after entering a valid User ID and Organization ID, the user is presented with the available methods of login upon clicking the “Continue” button. |  |  | User should show login method. Like: Password with OTP, Authenticator App, Email Token | Expected Result | Passed
CU-0.0.5 |  | Login | Ensure that after clicking on the “Password with OTP” option, the user is presented with a field to enter the OTP. |  |  | The user should be presented with an option to enter the OTP. | Expected Result | Passed
CU-0.0.6 |  | Login | Verify the error message should display after entering the invalid credentials. |  |  | Error message should display after entering the invalid credentials. | Expected Result | Passed
CU-0.0.7 |  | Login | Verify that the password entered should be in encrypted form. |  |  | Password should be entered in encrypted form | Expected Result | Passed
CU-0.0.8 |  | Login | Verify that the user can be able to view the password by clicking on the eye icon. |  |  | After click on eye icon user should view the password | Expected Result | Passed
CU-0.0.9 |  | Login | Verify that the user will get into their dashboard screen after login in with the correct credentials. |  |  | After logged in user should show Dashboard Screen | Expected Result | Passed
CU-0.0.10 |  | Login | Verify new captcha is generated in case the user adds the wrong captcha. |  |  | New captcha should be generated if the user adds the wrong captcha. | Expected Result | Passed
CU-0.0.11 |  | Login | Verify new OTP is generated in case the user adds the wrong OTP. |  |  | New OTP should be generated if the user adds the wrong OTP. |  | Not Executed
CU-0.0.12 |  | Login | Verify if OTP is not matching, it's give an error message |  |  | System should give an error message if OTP is not matched | Expected Result | Passed
CU-0.0.13 |  | Login | Verify an error message should be shown in case the captcha is not filled by the user or User add wrong OTP. |  |  | An error message should be shown if the user does not fill in the captcha/ user enters the wrong OTP. | Expected Result | Passed
CU-0.0.14 |  | Login | Verify that if the user adds the wrong OTP, then a Resend OTP option is available or not |  |  | There should be a visible option or button to resend the OTP, allowing the user to request a new OTP if user enter wrong OTP |  | Not Executed
CU-0.0.15 |  | Login | Verify that user id will be Lock after Multiple Invalid Login Attempts |  |  | 1. After the 5th consecutive invalid attempt, the user account should be locked, and the application should display a message indicating the account is locked for 5 minutes. 2. The user should not be able to log in with valid credentials until the 5-minute lockout period has expired. 3. After waiting 5 minutes, the user should be able to log in successfully with valid credentials. | Expected Result | Passed
CU-0.0.16 |  | Login | Password Reset Option for First-Time Login |  |  | Upon successful login, the user is presented with an option to reset their password. | Expected Result | Passed
CU-0.0.17 |  | Login | New Password Complexity Requirements |  |  | It should have following complexity requirements 1. must be at least 8 characters long. 2. must contain at least one special character. 3. must contain at least one uppercase letter and one lowercase letter. 4. must contain at least one digit. | System don't provide this option: 4. must contain at least one digit. | Passed
CU-0.0.18 |  | Login | Verify the displayed error message grammar should be correct. |  |  | Displayed error message grammar should be correct. | Expected Result | Passed
CU-0.0.19 |  | Login | Verify the login session timeout duration. So, once logged in a user cannot be authenticated for a lifetime. |  |  | User should not be authenticated for lifetime if session timeout is over | Expected Result | Passed
CU-0.0.20 | Profile Management | Profile Management | Ensure that after logging into the Corporate Internet Banking platform, the top right corner of the interface displays the correct user company and user-id. |  |  | The top right corner should display the user’s name and role. | Expected Result | Passed
CU-0.0.21 | Profile Management | Profile Management | Verify that Edit Profile option is correctly working or not |  |  | Edit Profile Option should correctly working |  | Not Executed
CU-0.0.22 | Profile Management | Profile Management | Verify Password Reset Option is correctly working or not |  |  | Password Reset Option should correctly working | Expected Result | Passed
CU-0.0.23 |  | Profile Management | Verify Old Password and New Password checking option, by giving same password in Password Reset Option |  |  | Password Reset Option should correctly working | Expected Result | Passed
CU-0.0.24 |  | Profile Management | Verify Password Time Duration field by giving negative, floating value |  |  | Password Time Duration should be in integer number |  | Failed | Picture
CU-0.0.25 |  | Profile Management | Verify the error message by giving wrong password in Old Password field |  |  | System should give proper error message, if the old password does not match with the new password |  | Failed | Picture
CU-0.0.26 |  | Dashboard | Ensure that after clicking the eye button, the visibility state (whether the amount is visible or hidden) is retained even if the mouse is moved to a different location. |  |  | The visibility state should persist (remain hidden) and should not be affected by mouse movement or focus loss. | Expected Result | Passed
CU-0.0.27 |  | Dashboard | Verifies Balances functionality on Dashboard |  |  | Clicking on each option should lead to the respective detailed view: CASA: Should display the current CASA accounts balance. FDR: Should display the current Fixed Deposit accounts balance. Loans: Should display the Loans accounts balance. | Expected Result | Passed
CU-0.0.28 |  | Dashboard | Verify that the balances update correctly in real-time |  |  | The displayed balances for CASA, Deposit, and Loans should update in real-time after the transaction is processed. | Not as Expected Result | Failed
CU-0.0.29 |  | Dashboard | Verify that the dashboard displays all requests initiated by the Maker, including relevant details such as request type, amount, destination account and Current Stage/Status of Requests. |  |  | The dashboard should list all the Maker's requests in an organized table or list format. Each request should include details like request type, amount, date/time of submission, destination account and Current Stage/Staus of requests. | Not as Expected Result | Failed
CU-0.0.30 |  | Dashboard | Test the dashboard’s ability to notify the Maker of any action required (e.g., resubmission for rejected requests). |  |  | The system should notify the Maker if any of their requests require further action, with a clear message displayed on the dashboard | Not as Expected Result | Failed
CU-0.0.31 |  | Dashboard | Verify that the Approver can reject a request in the Approver section without any issues. |  |  | 1. The system should allow the Approver to reject any pending request. 2. Upon rejection, the request should be removed from the Approver’s pending list and marked as Rejected in the system. 3. The Maker should receive a notification that the request has been rejected, including the reason for rejection. | Expected Result | Passed
CU-0.0.32 | Transaction | Single Transaction | Verify that only valid users have the rights to perform Single Transfer with their own bank or other banks. |  |  | 1. Valid users should be able to perform Single Transfers with both their own bank and other banks. 2. Invalid users should not be able to perform Single Transfers and should receive appropriate error messages. | Expected Result | Passed
CU-0.0.33 | Transaction | Single Transaction | Verify successful fund transfer between two accounts within the same bank. |  |  | Funds are transferred immediately, and both the sender and receiver’s balances are updated instantly. | Expected Result | Passed
CU-0.0.34 | Transaction | Single Transaction | Verify that the selected source account correctly displays the Account Title, Account Balance, Remaining Number of Transactions for the day, and Remaining Transaction Limit for the day. |  |  | The selected source account should show the correct A/C Title, A/C Balance, and Remaining No of Trans. Today, Remaining Trans. Limit Today | Expected Result | Passed
CU-0.0.35 | Transaction | Fund Transfer | Verify that security features like OTP or 2FA are implemented and required for transaction authorization. |  |  | Users should complete the OTP or 2FA process to authorize the transaction. | Expected Result | Passed
CU-0.0.36 | Transaction | Fund Transfer | Ensure that the system updates the transaction status accurately (e.g., pending, completed). |  |  | The transaction status should reflect its actual state throughout the process. | Expected Result | Passed
CU-0.0.37 | Transaction | Fund Transfer | Verify that no incoming credit transactions can be processed on the destination account when credit freeze is active |  |  | The transfer should fail and an error message should be displayed stating that Account 'B' is under credit freeze and can't receive deposits. |  | Not Executed
CU-0.0.38 | Transaction | Fund Transfer | Verify that no outgoing debit transactions can be processed on the source account when debit freeze is active |  |  | The transfer should fail and an error message should be displayed stating that Account 'A' is under debit freeze and can't process outgoing transactions |  | Not Executed
CU-0.0.39 | Transaction | Fund Transfer -> Transfer (Own Bank) | Verify that only registered source accounts are displayed in the drop-down list for fund transfer |  |  | The drop-down list should display only the registered source accounts that are linked to the user’s profile. The list should not include any unregistered or unauthorized accounts. | Expected Result | Passed
CU-0.0.40 | Transaction | Fund Transfer -> Transfer (Own Bank) | Verify that the system handles and displays an error message for insufficient funds in the source account. |  |  | An appropriate error message should be shown if funds are insufficient for the transfer. | Not as Expected Result | Failed
CU-0.0.41 | Transaction | Fund Transfer -> Transfer (Own Bank) | Ensure that if a registered source account encounters a problem (e.g., account suspension or restriction, inactive, dormant, inoperative, garnish, deceased), it should not be selectable for fund transfers, and the system should display an appropriate error or alert message |  |  | An appropriate error or alert message should be displayed when the user attempts to select the problematic account, clearly indicating the reason for the issue (e.g., "This account is currently suspended and cannot be used for transactions."). |  | Not Executed
CU-0.0.42 | Transaction | Fund Transfer -> Transfer (Own Bank) | Verify that added beneficiaries are displayed in the destination account drop-down list during fund transfers. |  |  | After adding a beneficiary account, then if this beneficiary account status = active, then it should be shown in the destination drop-down list | Expected Result | Passed
CU-0.0.43 | Transaction | Fund Transfer -> Transfer (Own Bank) | Verify that inactive beneficiary accounts are not displayed in the destination account drop-down list. |  |  | After adding a beneficiary account, if this beneficiary account status = inactive, then it should not be shown in the destination drop-down list |  | Not Executed
CU-0.0.44 | Transaction | Fund Transfer -> Transfer (Own Bank) | Ensure that if a registered destination account encounters a problem (e.g., account suspension or restriction, inactive, dormant, inoperative, garnish, deceased), it should not be selectable for fund transfers, and the system should display an appropriate error or alert message |  |  | An appropriate error or alert message should be displayed when the user attempts to select the problematic account, clearly indicating the reason for the issue (e.g., "This account is currently suspended and cannot be used for transactions."). |  | Not Executed
CU-0.0.45 | Transaction | Fund Transfer -> Transfer (Own Bank) | Verify if user inputs unregistered or unauthorized accounts then error/alert message is showing or not |  |  | An appropriate error or alert message should be displayed if user enter an unregistered or an unauthorized account number | It is showing error message | Failed
CU-0.0.46 | Transaction | Fund Transfer -> Transfer (Own Bank) | Verify Amount field |  |  | The Amount field should only accept numeric values and display them with comma separation (e.g., 1,000, 50,000) | Expected Result | Passed
CU-0.0.47 | Transaction | Fund Transfer -> Transfer (Own Bank) | Verify Amount field before proceed |  |  | The system should reject any non-numeric or incorrectly formatted inputs, providing clear error or validation messages (e.g., "Invalid amount. Please enter a numeric value.") | Not as Expected Result | Failed
CU-0.0.48 | Transaction | Fund Transfer -> Transfer (Own Bank) | Verify that the transfer limit validation is applied consistently across different source accounts and destination account |  |  | The system should display a clear and informative error message that explains the reason for rejection (e.g., "Transfer amount exceeds your permitted limit of 1,000. Please enter a valid amount.") | Not as Expected Result | Failed
CU-0.0.49 | Transaction | Fund Transfer -> Transfer (Own Bank) | Verify Remarks (Optional) field |  |  | It should be text type field | Expected Result | Passed
CU-0.0.50 | Transaction | Fund Transfer -> Transfer (Own Bank) | Verify Proceed Button |  |  | After click on the proceed button a pop-up screen should displayed for entering OTP | Expected Result | Passed
CU-0.0.51 | Transaction | Fund Transfer -> Transfer (Own Bank) | Verify Resend OTP button is working properly or not |  |  | Resend OTP button should work properly |  | Not Executed
CU-0.0.52 | Transaction | Fund Transfer -> Transfer (Own Bank) | Verify that the system displays an appropriate error message when the user enters an incorrect OTP during a transaction or authentication process. |  |  | 1. The system should display a clear and descriptive error message such as "Invalid OTP. Please try again." 2. The user should be prompted to re-enter the OTP or request a new OTP if multiple incorrect attempts are made. 3. The system should not proceed with the transaction until a correct OTP is entered. | Not as Expected Result | Failed
CU-0.0.53 | Transaction | Fund Transfer (Bulk) | Verify that only valid users have the right to perform Bulk transfers with their own bank or other banks. |  |  | 1. Valid users should be able to perform Bulk Transfers with both their own bank and other banks. 2. Invalid users should not be able to perform Bulk Transfers and should receive appropriate error messages. |  | Not Executed
CU-0.0.54 | Transaction | Fund Transfer (Bulk) | Ensure that the system allows the bulk transfer only if the available operating balance is sufficient. |  |  | The bulk transfer should proceed successfully if the account has enough balance to cover all the transactions. | Expected Result | Passed
CU-0.0.55 | Transaction | Fund Transfer (Bulk) | Test the system's behavior when the available balance is less than the total amount for the bulk transaction. |  |  | The system should block the transaction and display an error message indicating insufficient funds. | Expected Result | Passed
CU-0.0.56 | Transaction | Fund Transfer (Bulk) | Ensure that the system supports uploading an Excel file for bulk transfers and that the file is processed correctly. |  |  | The upload option should be present and functional within the bulk transfer section. | Expected Result | Passed
CU-0.0.57 | Transaction | Fund Transfer (Bulk) | Verify if the uploaded file has issues (e.g., incorrect format, missing data, etc.), review any error or validation messages provided by the system. |  |  | The system should display appropriate error messages or validation warnings if the file format is incorrect or if there are issues with the data. | Expected Result | Passed
CU-0.0.58 | Transaction | Fund Transfer (Bulk) | Verifies that the system correctly identifies and rejects invalid destination account entries when a user uploads an Excel file. |  |  | The system should display an error message indicating the presence of invalid destination accounts and prevent the file from being processed until corrections are made. The invalid entries should be clearly highlighted for the user. | Expected Result | Passed
CU-0.0.59 | Transaction | Fund Transfer (Bulk) | Verifies that the system correctly identifies and rejects duplicate destination account entries when a user uploads an Excel file. |  |  | The system should display an error message indicating the presence of duplicate destination accounts and prevent the file from being processed until corrections are made. The invalid entries should be clearly highlighted for the user. | Expected Result | Passed
CU-0.0.60 | Transaction | Fund Transfer (Bulk) | For Bulk Transfer, Ensure that the system allows downloading a properly formatted Excel file |  |  | Should download proper formatted excel file | Expected Result | Passed
CU-0.0.61 | Transaction | Fund Transfer (Bulk) | Check for the presence of an "Upload" button after selecting an Excel file. |  |  | An "Upload" button should be visible and enabled after a file is chosen, allowing the user to proceed with the upload. | Expected Result | Passed
CU-0.0.62 | Transaction | Fund Transfer (Bulk) | Verify that clicking the "Upload" button processes the selected Excel file and displays it in the file list. |  |  | After clicking "Upload," the system should successfully process the file and update the file list to include the newly uploaded Excel file. | Expected Result | Passed
CU-0.0.63 | Transaction | Fund Transfer (Bulk) | Ensure that the system prevents uploading an Excel file with a duplicate Reference Number. |  |  | If a user attempts to upload a file with an existing Reference Number, the system should display a warning message indicating that the upload is not allowed due to the duplicate Reference Number. |  | Not Executed
CU-0.0.64 | Transaction | Fund Transfer (Bulk) | Ensure that the system prevents uploading an Excel file if the Source Account Number is not selected. |  |  | If the user does not select a Source Account Number, the system should display an error message and prevent the upload, requiring the user to select a Source Account before proceeding. |  | Not Executed
CU-0.0.65 | Transaction | Fund Transfer (Bulk) | Verifies that the system prevents the transaction from proceeding if the user changes the source account after uploading an Excel file with a default source account. |  |  | The system should prevent the transaction from proceeding and display a warning message indicating that the source account has been changed and is not allowed. The user should be required to either revert the source account or update the Excel file accordingly before proceeding. |  | Not Executed
CU-0.0.66 | Transaction | Fund Transfer (Bulk) | Verify that uploaded excel file is deleting or not from the system |  |  | Uploaded Excel file should Delete properly after clicking on the Delete button and Before deleting it should show a warning message |  | Not Executed
CU-0.0.67 | Transaction | Fund Transfer -> Bulk Transfer (Own Bank) | Verify that only registered source accounts are displayed in the drop-down list for fund transfer |  |  | The drop-down list should display only the registered source accounts that are linked to the user’s profile. The list should not include any unregistered or unauthorized accounts. |  | Not Executed
CU-0.0.68 | Transaction | Fund Transfer -> Bulk Transfer (Own Bank) | Ensure that if a registered source account encounters a problem (e.g., account suspension or restriction, inactive, dormant, inoperative, garnish, deceased), it should not be selectable for fund transfers, and the system should display an appropriate error or alert message |  |  | An appropriate error or alert message should be displayed when the user attempts to select the problematic account, clearly indicating the reason for the issue (e.g., "This account is currently suspended and cannot be used for transactions."). |  | Not Executed
CU-0.0.69 | Transaction | Fund Transfer -> Bulk Transfer (Own Bank) | Verify that the selected source account correctly displays the Account Title, Account Balance, Remaining Number of Transactions for the day, and Remaining Transaction Limit for the day. |  |  | The selected source account should show the correct A/C Title, A/C Balance, and Remaining No of Trans. Today, Remaining Trans. Limit Today |  | Not Executed
CU-0.0.70 | Transaction | Fund Transfer -> Bulk Transfer (Own Bank) | Ensure that the system regularly checks for the status of destination accounts before executing transfers. |  |  | The system should perform a status check (suspended, dormant, etc.) on all destination accounts before processing a transfer and block any transactions to problematic accounts (e.g., account suspension or restriction, inactive, dormant, inoperative, garnish, deceased, etc.). |  | Not Executed
CU-0.0.71 | Transaction | Fund Transfer -> Bulk Transfer (Own Bank) | Verify Proceed Button |  |  | After click on the proceed button a pop-up screen should displayed for entering OTP | Expected Result | Passed
CU-0.0.72 | Transaction | Fund Transfer -> Bulk Transfer (Own Bank) | Verify Resend OTP button is working properly or not |  |  | Resend OTP button should work properly |  | Not Executed
CU-0.0.73 | Transaction | Fund Transfer -> Bulk Transfer (Own Bank) | Verify that the system displays an appropriate error message when the user enters an incorrect OTP during a transaction or authentication process. |  |  | 1. The system should display a clear and descriptive error message such as "Invalid OTP. Please try again." 2. The user should be prompted to re-enter the OTP or request a new OTP if multiple incorrect attempts are made. 3. The system should not proceed with the transaction until a correct OTP is entered. | Expected Result | Passed
CU-0.0.74 | Transaction | Fund Transfer -> Transfer (Other Bank) Through BEFTN | Verify the successful initiation of a BEFTN transfer to another bank. |  |  | The funds should be transferred within 1-2 working days, and the user should receive confirmation of the transaction being processed. | Expected Result | Passed
CU-0.0.75 | Transaction | Fund Transfer -> Transfer (Other Bank) Through BEFTN | Validate the system’s handling of the EFT delay (1-2 working days) and notification to the user. |  |  | The system should inform the user about the expected delay, and the transaction should be marked as “Pending” until settled. |  | Not Executed
CU-0.0.76 | Transaction | Fund Transfer -> Transfer (Other Bank) Through BEFTN | Test the reversal mechanism when the beneficiary bank rejects the EFT due to incorrect details. |  |  | The transaction should be reversed, and the user should be notified of the failed transfer and refunded the amount. |  | Not Executed
CU-0.0.77 | Transaction | Fund Transfer -> Transfer (Other Bank) Through BEFTN | Verify that only registered source accounts are displayed in the drop-down list for fund transfer |  |  | The drop-down list should display only the registered source accounts that are linked to the user’s profile. The list should not include any unregistered or unauthorized accounts. | Expected Result | Passed
CU-0.0.78 | Transaction | Fund Transfer -> Transfer (Other Bank) Through BEFTN | Verify that the system handles and displays an error message for insufficient funds in the source account. |  |  | An appropriate error message should be shown if funds are insufficient for the transfer. | Not as Expected Result | Failed
CU-0.0.79 | Transaction | Fund Transfer -> Transfer (Other Bank) Through BEFTN | Ensure that if a registered source account encounters a problem (e.g., account suspension or restriction, inactive, dormant, inoperative, garnish, deceased), it should not be selectable for fund transfers, and the system should display an appropriate error or alert message |  |  | An appropriate error or alert message should be displayed when the user attempts to select the problematic account, clearly indicating the reason for the issue (e.g., "This account is currently suspended and cannot be used for transactions."). |  | Not Executed
CU-0.0.80 | Transaction | Fund Transfer -> Transfer (Other Bank) Through BEFTN | Verify options for destination account in fund transfers. |  |  | 1. An input field should be available for the user to manually enter an account number. 2. A list of beneficiaries that the user has previously added should be shown. |  | Not Executed
CU-0.0.81 | Transaction | Fund Transfer -> Transfer (Other Bank) Through BEFTN | Verify that added beneficiaries are displayed in the destination account drop-down list during fund transfers. |  |  | After adding a beneficiary account, then if this beneficiary account status = active, then it should be shown in the destination drop-down list | Expected Result | Passed
CU-0.0.82 | Transaction | Fund Transfer -> Transfer (Other Bank) Through BEFTN | Verify that inactive beneficiary accounts are not displayed in the destination account drop-down list. |  |  | After adding a beneficiary account, if this beneficiary account status = inactive, then it should not be shown in the destination drop-down list | Expected Result | Passed
CU-0.0.83 | Transaction | Fund Transfer -> Transfer (Other Bank) Through BEFTN | Ensure that if a registered destination account encounters a problem (e.g., account suspension or restriction, inactive, dormant, inoperative, garnish, deceased), it should not be selectable for fund transfers, and the system should display an appropriate error or alert message |  |  | An appropriate error or alert message should be displayed when the user attempts to select the problematic account, clearly indicating the reason for the issue (e.g., "This account is currently suspended and cannot be used for transactions."). |  | Not Executed
CU-0.0.84 | Transaction | Fund Transfer -> Transfer (Other Bank) Through BEFTN | Verify if user inputs unregistered or unauthorized accounts then error/alert message is showing or not |  |  | An appropriate error or alert message should be displayed if user enter an unregistered or an unauthorized account number | Expected Result | Passed
CU-0.0.85 | Transaction | Fund Transfer -> Transfer (Other Bank) Through BEFTN | Verify Amount field |  |  | The Amount field should only accept numeric values and display them with comma separation (e.g., 1,000, 50,000) | Not as Expected Result | Failed
CU-0.0.86 | Transaction | Fund Transfer -> Transfer (Other Bank) Through BEFTN | Verify Amount field before proceed |  |  | The system should reject any non-numeric or incorrectly formatted inputs, providing clear error or validation messages (e.g., "Invalid amount. Please enter a numeric value.") | Not as Expected Result | Failed
CU-0.0.87 | Transaction | Fund Transfer -> Transfer (Other Bank) Through BEFTN | Verify display of banks under Corporate Account |  |  | The system should display a complete and accurate list of banks available under the corporate account | Expected Result | Passed
CU-0.0.88 | Transaction | Fund Transfer -> Transfer (Other Bank) Through BEFTN | Verify display of Branches under selected Bank |  |  | Upon selecting a bank, the system should display only the branches associated with the selected bank. | Expected Result | Passed
CU-0.0.89 | Transaction | Fund Transfer -> Transfer (Other Bank) Through BEFTN | Verify that the transfer limit validation is applied consistently across different source accounts and destination account |  |  | The system should display a clear and informative error message that explains the reason for rejection (e.g., "Transfer amount exceeds your permitted limit of 1,000. Please enter a valid amount.") | Not as Expected Result | Failed
CU-0.0.90 | Transaction | Transaction History | Checking Transaction history from a certain date |  |  | System should show a list between that period of time | Expected Result | Passed
CU-0.0.91 | Transaction | Transaction History | Checking "To Date" greater than the "From Date" |  |  | System shouldn't allow user to set "To date greater than the Form Date | Expected Result | Passed
CU-0.0.92 | Transaction | Transaction History | Checking "Reset" button works properly |  |  | Reset button should reset the given date | Expected Result | Passed
CU-0.0.93 | Transaction | Transaction History | Checking "Search" button works properly |  |  | Search button should search the transaction between the set date | Expected Result | Passed
CU-0.0.94 | Transaction | Transaction History | Transaction heading and the informations should be in right format with alignment |  |  | Heading and the information should be in right format with proper alignment | Expected Result | Passed
CU-0.0.95 | Transaction | Transaction History | Checking by selecting "Items per page" works properly |  |  | System should shows information according to selected "Items per page" number | Expected Result | Passed
CU-0.0.96 | Transaction | Transaction History | Checking Back and Reverse icon works properly |  |  | Back icon should back the pervious Items Reverse icon should shows the next items | Expected Result | Passed
| Cheque Management | Cheque Book Request | Checking Select Account should be in a list |  |  | System should provide a list of source account which is saved | Expected Result | Passed
| Cheque Management | Cheque Book Request | Checking Receiving Branch is based on the Selected Account |  |  | System should provide a list of Branch based on the source account | Expected Result | Passed
| Cheque Management | Cheque Book Request | Checking the Cheque Leaf No based on the Account number |  |  | System should provide a list of Cheque Leaf number based on the source account | Expected Result | Passed
| Cheque Management | Cheque Book Request | Checking the Remarks field is textable filed |  |  | System should allow user to input text on this field | Expected Result | Passed
| Cheque Management | Cheque Book Request | Checking the "Reset" button clear the content on this page |  |  | Reset button should reset the page and allow user to input the information | Expected Result | Passed
| Cheque Management | Cheque Book Request | Checking the "Proceed" button clear the content on this page |  |  | Proceed button should allow user to poceed the information and allow user for next steps | Expected Result | Passed
CU-0.0.97 | Cheque Management | Stop A Cheque | Checking Source Account should be in a list of all saved accounts |  |  | System should provide a list of source account which is saved | Expected Result | Passed
CU-0.0.98 | Cheque Management | Stop A Cheque | Checking the Leaf number is in dropdown list |  |  | System should provide a list of numbers on the cheque based on the source account | Expected Result | Passed
CU-0.0.99 | Cheque Management | Stop A Cheque | Checking Cheque Reason field for Stop a Account |  |  | System should allow user to set a reason to stop a cheque | Expected Result | Passed
CU-0.0.100 | Cheque Management | Stop A Cheque | Checking submit a request for stop a cheque |  |  | System should proceed the request and stop the cheque | Expected Result | Passed
CU-0.0.101 | Cheque Management | Stop A Cheque | Checking proceed a request without selecting Leaf number for stop a cheque |  |  | System should pop-up an error message | Expected Result | Passed
CU-0.0.102 | Cheque Management | Stop A Cheque | Checking Source Account should be in a list of all saved accounts |  |  | System should provide a list of source accounts that are previously added | Expected Result | Passed
CU-0.0.103 | Cheque Management | Stop A Cheque | Checking "Cancel" button cancel the request and refresh the page |  |  | System should refresh the page | Not as Expected Result | Failed | #VALUE!
CU-0.0.104 | Cheque Management | Cheque Status | Checking the status of that account between the selected date |  |  | System should provide the status list of that selected account | Expected Result | Passed
CU-0.0.105 | Cheque Management | Cheque Status | Checking by Search an account when source account is not selected |  |  | System should be an error message if source ac is not selected | Not as Expected Result | Failed | #VALUE!
CU-0.0.106 | Cheque Management | Cheque Status | Checking Cheque Status Information by given filter |  |  | System should format the list according to filter option | Expected Result | Passed
CU-0.0.107 | Cheque Management | Cheque Status | Checking the Form date and To date |  |  | From Date: should not be select future date To Date: should not be select greater than From Date | Expected Result | Passed
CU-0.0.108 | Corporate Banking | About | Verifying the responsiveness of the page |  |  | Page should be responsive | Expected Result | Passed
CU-0.0.109 | Corporate Banking | About | Verifying the allingment of the page |  |  | Context should be in right allingment as per SRS | Expected Result | Passed
CU-0.0.110 | Corporate Banking | About | Checking every module button works properly |  |  | System should shows context on by selecting modules: General Corporate Finance, Work Order Financing, Export Finance, Project Finance, Cash Management, Syndication Finance | Expected Result | Passed
CU-0.0.111 | Corporate Banking | About | Checking page context according to selected button |  |  | Page's context should be releated according to the selected button | Expected Result | Passed

## Report
Test Case Report
Project Name | Corporate Internet Banking
Module Name | Corporate User
Test Case Version | V-0.0.2
Written By | Afrida Rahman
Executed By | Afrida Rahman
Date | 20/10/2024
Reviewed By | N/A
TEST EXECUTION REPORT
Test Case Cycle No. | PASS | FAIL | Not Executed (has Dependencies for Failed cases) | Out Of Scope | Total TC
Cycle - 2 | 77 | 16 | 24 | 0 | 117
Cycle - 3 | #REF! | #REF! | #REF! | #REF! | #REF!
Cycle - 4 | #REF! | #REF! | #REF! | #REF! | #REF!
LIMITATIONS
Documents |  |  |  | Received | Useful
FSD |  |  |  | YES | YES
USER STORY |  |  |  | YES | YES
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Test_Matrix
Metrics | Description | Test Cycle - 2 Result(%)
Percentage of Test cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | 79.4872
Percentage of Test cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | 20.5128
Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | 65.812
Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | 13.6752
Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | 0
Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
Defect Removal Efficiency | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
Defect Age | Fixed date - Reported date | N/A
Customer Satisfaction | No. of complaints per Period of Time | N/A

## Bug_Report_1
SL# | Observation Date | Module | Role | Feature | Bug Description | Expected Result | Actual Result | Attachments | Remarks | Interface Type | Severity | Go Live Critical | Rank | Issue Type | Recommended Solution | Delivery Status | Planned Delivery Date | Actual Delivery Date | Developer Name | Reviewer Name | Dev Status | Planned Dev Start Date | Planned Dev Completion Date | Actual Dev Start Date | Actual Dev Completion Date | Re-Test Status | Tester Name | Test Cycle | Test Start Date | Test End Date | Tester Comments | Customer Feedback | Feedback Date | Reason | Review Status (local serv.) | Review Remarks
17 | 20/10/2024 | Corporate-User | User-Maker | Change Password | System should give proper alert message if “Old Password” is not matched. and the “Reset Password Duration” should be in integer number | Currently System accept decimal number in Duration time | Not as expected | if the old password does not match with the new password, system should give proper error message |  |  |  | Critical |  | Bug | [12 empty] | Afrida Rahman | 1 | 20/10/2024 | 21/10/2024
18 | 20/10/2024 | Corporate-User | User-Maker | Transaction History | System shouldn't allow user to set "To Date” greater than the “Form Date”. There should be a date validation | Currently System allow user to set To date less than From date | Not as expected | To Date should be greater than the From Date in Transaction History |  |  |  | Critical |  | Bug |  |  |  |  | Abeer |  | Done | [5 empty] | Afrida Rahman | 1 | 20/10/2024 | 21/10/2024
19 | 20/10/2024 | Corporate-User | User-Maker | Stop A Cheque | "Cancel" button should cancel the request and refresh the page | Currently cancel button don't do any action | Not as expected | cancle button should refresh the page in Stop A Cheque module |  |  |  | Critical |  | Bug |  |  |  |  | Abeer |  | Done | [5 empty] | Afrida Rahman | 1 | 20/10/2024 | 21/10/2024
20 | 20/10/2024 | Corporate-User | User-Maker | Stop A Cheque | System should give a pop-up error message if source account is not selected | Currently system don't do any action | Not as expected | system should be an error message if source ac is not selected |  |  |  | Critical |  | Bug |  |  |  |  | Abeer |  | Done | [5 empty] | Afrida Rahman | 1 | 20/10/2024 | 21/10/2024
21 | 20/10/2024 | Corporate-User | User-Maker | Stop A Cheque | There should be a validation in “Form Date” and “To Date” | Currently System allow user to set To date less than From date | Not as expected | From date and To date should not be in future and past, there should be a validation |  |  |  | Critical |  | Bug |  |  |  |  | Abeer |  | Done | [5 empty] | Afrida Rahman | 1 | 20/10/2024 | 21/10/2024
22 | 24/10/2024 | Transactions (Single Transaction) | User-Maker | Single Transaction - Own Bank | Giving amount in decimal number, but system only transfer integer value of amount | System should accept decimal number of ammount | Not as expected | Decimal Balance-Maker-Own Module-Transaction module https://erainfotechbd-my.sharepoint.com/:i:/p/afrida/EXkb27YsxKBMviKE3zKk7mUBf6KlqvcaFvaDzQip7fUFdg?e=gRvjQt |  |  |  | Critical |  | Bug |  |  |  |  | Abeer |  | Done | [5 empty] | Afrida Rahman | 1 | 23/10/2024 | 24/10/2024
23 | 24/10/2024 | Transactions (Single Transaction) | User-Maker | Single Transaction - Own Bank | Transfer from Own Bank by giving invalid Destination A/C | Pop-up error message should be specific if Destination AC is not correct | Not as expected | error should be specific if Destination AC is not correct |  |  |  | Critical |  | Bug |  |  |  |  | Abeer |  | Done | [5 empty] | Afrida Rahman | 1 | 23/10/2024 | 24/10/2024
24 | 24/10/2024 | Transactions (Single Transaction) | User-Maker | Single Transaction - Own Bank | Destination AC error message should be more readable for enduser if account is not selected | Pop-up error message should be specific for not selected Destination AC | Not as expected | not selected Destination AC error message should be more readable for enduser |  |  |  | Critical |  | Bug |  |  |  |  | Abeer |  | Done | [5 empty] | Afrida Rahman | 1 | 23/10/2024 | 24/10/2024
25 | 24/10/2024 | Transactions (Single Transaction) | User-Maker | Single Transaction - Own Bank | Checking the validation before procced by giving invalid Destination A/C in Transfer from Own Bank module | System should validate the invalid Destination AC before proceed the request | Not as expected | System should validate the invalid Destination AC before proceed the request |  |  |  | Critical |  | Bug |  |  |  |  | Abeer |  | Done | [5 empty] | Afrida Rahman | 1 | 23/10/2024 | 24/10/2024
26 | 24/10/2024 | Transactions (Single Transaction) | User-Maker | Single Transaction - Own Bank | Edit the selected Source A/C and proceed the request | 1. Error should be in specific 2. Selected account should not be editable from the Source AC dropdown list | Not as expected | error should be in specific and selected account should not editable from the Source AC dropdown list |  |  |  | Critical |  | Bug |  |  |  |  | Abeer |  | Done | [5 empty] | Afrida Rahman | 1 | 23/10/2024 | 24/10/2024
27 | 24/10/2024 | Transactions (Single Transaction) | User-Maker | Single Transaction - Other Bank | Amount field should not allow to giving text and character | Before proceed, System should not allow user to set except number | Not as expected | BEFTN-Transaction-OtherBank-BEFTN-save |  |  |  | Critical |  | Enhancement |  |  |  |  | Abeer |  | Done | [5 empty] | Afrida Rahman | 1 | 23/10/2024 | 24/10/2024
28 | 24/10/2024 | Transactions (Single Transaction) | User-Maker | Single Transaction - Other Bank | AC Title field should not editable | AC Title, Bank, Branch should not editable in Transaction BEFTN | Not as expected | AC Title should not editable in Transaction BEFTN.png |  |  |  | Critical |  | Enhancement |  |  |  |  | Abeer |  | Done | [5 empty] | Afrida Rahman | 1 | 23/10/2024 | 24/10/2024
29 | 24/10/2024 | Transactions (Single Transaction) | User-Maker | Single Transaction - Other Bank | Source Account field should be in read-only field | 1. Source Account should not editable, should be in read-only field 2. Error message should be clear BEFTN | Not as expected | Source AC should not editable AND Error message should be clear BEFTN.png |  |  |  | Critical |  | Bug |  |  |  |  | Abeer |  | Done | [5 empty] | Afrida Rahman | 1 | 23/10/2024 | 24/10/2024
30 | 24/10/2024 | Transactions (Single Transaction) | User-Maker | Single Transaction - Other Bank | By giving Destination Account number, system shows the information for that account user | There should be validation with Destination Account. By giving Destination Account number, system shows the information for that account user | Not as expected | There should be validation with Destination AC BEFTN.png |  |  |  | Critical |  | Bug | [12 empty] | Afrida Rahman | 1 | 23/10/2024 | 24/10/2024
31 | 24/10/2024 | Transactions (Single Transaction) | User-Maker | Single Transaction - Other Bank | "Amount" value larger than the "Remaining Trans. Limit Today" amount value | There should be a validation in "Remaining Trans. Limit Today" and the "Amount" | Not as expected | Transaction limit not matches with the DayRemaining limit.png |  |  |  | Critical |  | Bug | [12 empty] | Afrida Rahman | 1 | 23/10/2024 | 24/10/2024
32 | 24/10/2024 | Transactions (Single Transaction) | User-Maker | Single Transaction - Own Bank | Destination AC details should be added to Transfer(Own Bank) | System should added to Destination AC details to Transfer(Own Bank) | Not as expected | Destination AC details should be added to Transfer(Own Bank) module.png |  |  |  | Critical |  | Bug | [12 empty] | Afrida Rahman | 1 | 23/10/2024 | 24/10/2024
33 | 24/10/2024 | Transactions (Single Transaction) | User-Maker | Single Transaction - Own Bank | Invalid OTP should give alert message in Checker and Maker User | System should give alert message in Checker and Maker User invalid OTP | Not as expected | invalid OTP should give an alert message.png |  |  |  | Critical |  | Bug |  |  |  |  | Abeer |  | Done | [5 empty] | Afrida Rahman | 1 | 23/10/2024 | 24/10/2024
34 | 24/10/2024 | Transactions (Single Transaction) | User-Maker | Transaction History | Set a future date in "To Date" option in Transaction History | System should not allow to set future date in To Date option in Transaction History | Not as expected | System should not allow to set future date in To Date option in Transaction History.png |  |  |  | Non-Critical |  | Bug |  |  |  |  | Abeer |  | Done | [5 empty] | Afrida Rahman | 1 | 23/10/2024 | 24/10/2024
35 | 24/10/2024 | Transactions (Single Transaction) | User-Maker | Single Transaction - Own Bank | After a successful transaction the "Remaining No of Trans. Today" and "Remaining Trans. Limit Today" should be updated | System should updated the Limit and Remain Transaction should be updated | Not as expected | After a successful transaction the Remain Tran and Tran Limit should be updated.png |  |  |  | Critical |  | Bug | [12 empty] | Afrida Rahman | 1 | 23/10/2024 | 24/10/2024
36 | 24/10/2024 | Transactions History | User-Checker | Dashboard | After approve a request page should auto refresh and show updated information | System should auto refresh and show updated information, after approve a request page | Not as expected | After approve a request page should auto refresh and show updated information.png |  |  |  | Non-Critical |  | Enhancement |  |  |  |  | Abeer |  | Done | [5 empty] | Afrida Rahman | 1 | 23/10/2024 | 24/10/2024
37 | 24/10/2024 | Transactions (Bulk Transaction) | User-Maker | Bulk Transfer (Own Bank) | Error in source AC information details | System should give all details information based on the Source Account | Not as expected | error source AC information details in BulkTransaction.png |  |  |  | Critical |  | Bug |  |  |  |  | Abeer |  | Done | [5 empty] | Afrida Rahman | 1 | 23/10/2024 | 24/10/2024
38 | 24/10/2024 | Transactions (Bulk Transaction) | User-Maker | Bulk Transfer (Own Bank) | Wrong error message, as Souce AC is already selected | System should give valid error message | Not as expected | wrong error message, as Souce AC is already selected |  |  |  | Critical |  | Bug |  |  |  |  | Abeer |  | Done | [5 empty] | Afrida Rahman | 1 | 23/10/2024 | 24/10/2024

## Bug_Report_2
SL# | Observation Date | Module | Role | Feature | Bug Description | Expected Result | Actual Result | Attachments | Remarks | Interface Type | Severity | Go Live Critical | Rank | Issue Type | Recommended Solution | Delivery Status | Planned Delivery Date | Actual Delivery Date | Developer Name | Reviewer Name | Dev Status | Planned Dev Start Date | Planned Dev Completion Date | Actual Dev Start Date | Actual Dev Completion Date | Re-Test Status | Tester Name | Test Cycle | Test Start Date | Test End Date | Tester Comments | Customer Feedback | Feedback Date | Reason | Review Status (local serv.) | Review Remarks
1 | 21/10/2024 | Corporate-User | Maker | Transaction Own Bank | Error message should be more specific in Transaction | System should not give error in transaction from own bank | Not as expected | transaction error in Transaction Own Branch.png |  |  |  | Non-Critical |  | Bug | [12 empty] | Afrida Rahman | 2 | 21/11/2024
2 | 21/10/2024 | Corporate-User | Maker | Transaction Own Bank | Transaction amount should not more than the a/c balance | system should check the remaining balance and add a validation error before proceed | Not as expected | transaction amount should not more than the remain balance.png |  |  |  | Critical |  | Bug | [12 empty] | Afrida Rahman | 2 | 21/11/2024
3 | 21/10/2024 | Corporate-User | Maker | Transaction Own Bank | "OK" button is invisible | "OK" button should be visible | Not as expected | after own bank transaction the Ok button should be visible in Transfer Own Bank.png |  |  |  | Non-Critical |  | Bug | [12 empty] | Afrida Rahman | 2 | 21/11/2024
4 | 21/10/2024 | Corporate-User | Checker and Approver | Transaction Own Bank | bank code, branch code is missing | bank code, branch code should be added according to a/c details | Not as expected | bank code, branch code should be add to checker and approver in Transfer own bank.png |  |  |  | Critical |  | Bug | [12 empty] | Afrida Rahman | 2 | 21/11/2024
5 | 21/10/2024 | Corporate-User | Approver | Transaction Own Bank | facing error in approve transaction in decemal number | system should allow user to approve transaction in any number | Not as expected | approver cannot approve the transaction Own Bank.png |  |  |  | Critical |  | Bug | [12 empty] | Afrida Rahman | 2 | 21/11/2024
6 | 21/10/2024 | Corporate-User | Approver | Transaction Own Bank | system accept Transaction amount more than the a/c remain balance | system should give alert, and add a validation Transaction amount with the a/c remain balance | Not as expected | system should give alert as amount is not enough in balance.png |  |  |  | Critical |  | Bug | [12 empty] | Afrida Rahman | 2 | 21/11/2024
7 | 21/10/2024 | Corporate-User | Approver | Transaction Own Bank | before giving OTP system should give alert | system should give alert and add a validation | Not as expected | before giving OTP system should validate the amount and error should be specific.png |  |  |  | Critical |  | Bug | [12 empty] | Afrida Rahman | 2 | 21/11/2024
8 | 21/10/2024 | Corporate-User | Approver | Transaction Own Bank | after successful transaction the amount should be less than before | a/c balance should be calculated | Not as expected | after successful transaction the total amount should be less than before.png |  |  |  | Critical |  | Bug | [12 empty] | Afrida Rahman | 2 | 21/11/2024
9 | 21/10/2024 | Corporate-User | Approver | Transaction Other Bank | Transaction should be done properly | System should allow user to transaction done properly | Not as expected | Transfer other bank 90tk error.png |  |  |  | Critical |  | Bug | [12 empty] | Afrida Rahman | 2 | 21/11/2024